## a. Detail M&E Plan Instructions
LWR Detailed M&E Plan Instructions
1. Complete the M&E Plan Matrix. It can be developed within the tab or developed in a word document and transferred to the M&E Plan Matrix tab.
a. For detailed instructions on completing the content of the M&E Plan Matrix, please refer to tab #3 M&E Plan Matrix Cheat Sheet.
b. Enter the objective statements and indicators ONLY in the M&E Plan Matrix. They are automatically linked to the Indicator Tracking Table and the Activity Tracking Tables.
2. Complete the Indicator Tracking Table (ITT)
a. Fill in the project name and the Project Year (PY) for the ITT. This workbook contains linked ITT and Activity Tracking Tables for up to a three year project.
b. Fill in the baseline values for each indicator including the date it was collected and the unit of measurement. If the baseline values do not come from a consolidated baseline survey, note in the comments where the values are archived (the document, file, government database, etc). The baseline values are automatically populated in the Year 2 and Year 3 ITTs.
3. Set indicator targets
a. Indicators targets should be set for each indicator based upon the details outlined in the project proposal taking into consideration timelines, number of staff, and budget. Start with Life of Project targets, then annual targets, then quarterly targets. Targets should be linked directly to the projects work plan/detailed implementation plan
§ ALL targets and actuals should be cumulative. This means that targets and actuals recorded for each quarter are reflecting what has been targeted or achieved to date. If a given indicator cannot be recorded in a cumulative manner for some reason, please place an asterisk beside it or include a note in the indicator notes box.
§ Values for indicators should be numeric with narrative reserved for the Narrative Report.
§ Life of project targets will be included in each ITT on an annual basis. The LOP targets should remain the same throughout, but in each new annual ITT any cumulative data should be transferred.
§ Impact indicators (outcome and goal) are often measured at the start of project (baseline) and end of project (endline) and therefore will only require Life of Project (LOP) targets.
b. The values in the "Target"and "Actual" columns should be entered as whole numbers, not percentages. This will help to ensure that the numerator and denominator are clearly expressed, which reduces calculation errors.
c. Formulas can be used in Excel so that percentages and other information calculate automatically, theoretically reducing the amount of data that must be entered manually. However, formulas can be tricky and should be double-checked to ensure that the data has been calculated in the way that it should.
4. Using the Indicator Tracking Table (ITT)
a. Actual data reported should be confirmed data that has been collected during the reporting period, not estimates or guesses. If you are confused about what an indicator means or how to enter the data, refer to your project’s M&E Plan Matrix.
b. The ITT should be filled out on a quarterly basis, before starting work on the Project Progress Report
c. Some indicators will require the roll-up of data from multiple communities, districts, regions, etc. The data from each individual source should be kept in a table on another tab within this file, with the sum linked to the Actual column for that indicator. This will help assist in data verification.
d. Make sure to update actual beneficiary numbers in the ITT in each project reporting period.
5. Complete the Activity Tracking Table (ATT): The Activity Tracking Table is a complimentary tool to the Indicator Tracking Table. It allows activities to be tracked in a summary manner in a separate tab so that the progress towards the project indicators in the ITT can be more easily read. The Activity Progress Summary row in the ATT, which sums up the progress on all activities linked to an Output, is linked to the Activity Progress Summary row in the ITT. See tab #8 for further instructions on using the ATT.
a. List the high level projects activities in the first column that were outlined in the project proposal. Make sure that the activities listed under each Output are linked specifically to that Output.
b. Complete the "targets" for each activity for each reporting period, year, and life of project based upon the project's detailed implementation plan.
c. Each reporting period, fill in the actual number of activities completed.
d. Each reporting period, update the status of the activity in column W. It should be updated with "not yet started," In progress," or "completed." If it is completed, list the date completed.
e. Ensure the Activity Progress Summary from the ATT has linked properly with the Activity Progress Summary for the same Output in the ITT.

## b. M&E Plan Matrix Description
TOOL SUMMARY: M&E PLAN MATRIX CHEAT SHEET
Purpose | The purpose of this tool is to guide staff on how to complete each column of the M&E Plan Matrix.
§ The M&E Plan Matrix is a critical tool for planning and managing data collection, analysis, and use. It expands the Logframe to identify key information requirements for each indicator and summarizes the key M&E tasks for the project.
o It helps staff to determine if the proposed indicators can effectively measure the result with which it is linked.
o It helps staff determine if it is feasible, in terms of resources and time, to collect data on the proposed indicators.
§ It includes: Full List of Indicators with detailed definitions, Data Sources/Tools, Frequency & Schedule, Responsible Person/Team, Data Analysis, Information Use/Audience, Reporting
§ The M&E Plan Matrix is nearly identical to USAID’s Performance Monitoring Plan. The instructions for the M&E Plan Matrix can be applied to complete USAID’s PMP.
Information Sources | 1. Logframe
2. Project Proposal (Initial M&E Plan)
Who | This tool should be completed by the project manager (partner) with participation from other key project staff. Upon completion by the project team, the completed M&E Plan Matrix should be submitted to the LWR Regional Monitoring and Evaluation Manager and LWR Program Manager for review and feedback.
When | Given that M&E Plan Matrix helps in defining the scope (cost, time) of the project’s monitoring system, it is recommended that the Indicator Definition, Frequency/Schedule, and Responsible Person columns be completed before finalizing the project proposal.
The remaining columns of the M&E Plan Matrix should be completed within the following timeframes:
§ Projects 1 year or less: complete a detailed M&E plan within 30 days of the project approval
§ Projects with a duration of 1-3 years: complete a detailed M&E plan within 60 days of the project approval
§ Projects with a duration of 3-5 years: complete a detailed M&E plan within 90 days of project approval
Recommendations | § SMART Criteria:
o It is recommended that objective statements in the Logframe are NOT written using SMART criteria.
- Nevertheless, SMART objective statements can sometimes be used effectively within project proposals to show all the details of the expected result in one statement.
o SMART criteria should be applied to indicators, not objective statements. (reference P. 37 of IFRC Project Planning Guidance Manual for further information on SMART criteria)
o Follow the instructions and examples for writing indicators found in the Logframe Cheat Sheet
o Additional SMART criteria for each indicator is detailed during completion of the M&E Plan Matrix
§ The M&E Plan Matrix is a living document and should be updated based upon relevant project adjustments
o If the M&E Plan Matrix is changed, report the changes, the reason, and how it affects other aspects of the M&E and project implementation plan
o If changes are made to the plan, ensure that HQ, the country office, and the partner have the updated version
§ This M&E Plan Matrix should be used for all LWR projects.
§ Ideally, the M&E Plan Matrix will be finalized during a joint project planning meeting (project kick-off meeting) with participation from both key partner and LWR staff.
Tips | § The M&E Plan Matrix should be completed by those who will be using it. This allows the project team to crosscheck the Logframe and indicators before project implementation (ensuring they are realistic to field realities and team capacities). Team involvement is essential because the M&E Plan Matrix requires their detailed knowledge of the project context, and their involvement reinforces their understanding of what data they are to collect and how they will collect them.
§ Keep the M&E Plan Matrix plan appropriate for the scale and timeframe of the project. Remember, it should be ‘good enough’.
§ Double check that your indicators can be measured in a realistic manner. Balance qualitative and quantitative data to measure indicators.
§ Make sure to be clear who within the project team is responsible for “owning the M&E Plan Matrix.” This includes ensuring it is thoroughly completed, that all relevant project stakeholders understand it and have copies of it, that any changes made are fully incorporated and shared, and to regularly monitor and manage that all outlined tasks are being completed. The same person should also be responsible for managing the Indicator Tracking Table and the Activity Tracking Table.

## c. M&E Plan Matrix Cheat Sheet
M&E Plan Matrix template was derived from IFRC’s M&E Plan Template (April 6, 2011): http://ifrc.org/en/who-we-are/performance-and-accountability/monitoring-and-evaluation/, and CRS’ ProPak III. The content for the instructions were borrowed primarily from IFRC’s M&E Plan Template (April 6, 2011) with additional content borrowed from CRS’ M&E in Emergencies, DESIGN: How to develop and M&E plan in an emergency project M&E Plan Template, Appendix 3, p. 54.

## d. M&E Plan Matrix Example
Project Name: |  | Project Location: |  |  | Project Year:
Identifier |  | Partner: |  |  | Project Start Date:
Project Sector(s): |  | Report Period: |  |  | Project End Date:
PERFORMANCE INDICATORS |  | DATA GATHERING |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Means of Verification | Frequency and Schedule | Reponsible person/ team | Data Analysis | Information Use/Audience | Reporting
Goal: The target population in the targeted priority action zone experience a reduction in deaths and injuries related to disasters
OUTCOME 1: Communities in the priority action zone have increased resiliency to climate change
Indicator 1.a: % increase in hectares of actively managed community mangrove forests by the end of the project (35% increase by end of project) | o Community managed land: land that has been given official government title as a public resource. o Actively managed: land has received a resource monitoring visit at least once a month o numerator = # hectares managed at yearly survey o denominator = # hectares managed at the beginning of the project | o government aerial survey o Community maps and site visits from field officers. o Community resource monitoring tracking data. | o Baseline data at beginning of project from most recent government aerial survey o Annually: monitoring data from annual government aerial survey o resource monitoring visit logs checked quarterly | o project manager o field officer | o Government data compared with community maps with participation from community disaster management committee and field officer within one week after government aerial surveys are completed. | o Help project staff determine is if community resource management is taking place and is effective o Annual progress report to LWR HQ and donor | o Annual cumulative progress report o endline report o quarterly project progess report (resource monitoring logs)
OUTPUT 1.1: Communities have an increased area of protected local mangrove resources
Indicator 1.1.a: % mangroves planted, alive one year after planting (75% after first year) | o numerator = # mangroves alive after 12 months o denominator = # mangroves planted | o CBOs tracking systems for growth rates and mortality rates of mangroves | o measured monthly for monitoring purposes o reported after data collection on month 12 after planting. | o community representatives, reported quarterly by country office | o Did any adverse weather events affect the mangroves? o What can be done to increase survival rate? | o Assist community in determining if mangroves planted are living or dying | o monthly monitoring reports o quarterly project progress reports o Final project report of cumulative data for all mangroves planted

## e. M&E Plan Matrix (Blank)
“Project Name” M&E Plan Matrix
Project Name: |  | Project Location: |  | Project Year
Identifier |  | Partner: |  |  | Project Start Date:
Project Sector(s): |  | Report Period: |  |  | Project End Date:
PERFORMANCE INDICATORS |  | DATA GATHERING |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Mean of Verification | Frequency and Schedule | Reponsible person/ team | Data Analysis | Information Use/Audience | Reporting Deadline
GOAL:
OUTCOME 1:
Indicator 1.a:
Indicator 1.b:
OUTPUT 1.1:
Indicator 1.1.a:
Indicator 1.1.b:
OUTPUT 1.2:
Indicator 1.2.a:
Indicator 1.2.b:
OUTCOME 2:
Indicator 2.a:
Indciator 2.b:
OUTPUT 2.1:
Indicator 2.1.a:
Indicator 2.1.b:
OUTPUT 2. 2:
Indicator 2.2.a:
Indicator 2.2.b:
OUTCOME 3:
Indicator 3.a:
Indciator 3.b:
OUTPUT 3.1:
Indicator 3.1.a:
Indicator 3.1.b:
OUTPUT 3. 2:
Indicator 3.2.a:
Indicator 3.2.b:
OUTCOME 4:
Indicator 4.a:
Indciator 4.b:
OUTPUT 4.1:
Indicator 4.1.a:
Indicator 4.1.b:
OUTPUT 4.2:
Indicator 4.2.a:
Indicator 4.2.b:
Note on A7: The content in Column A is linked to the ITT. This makes the content entered here automatically copied to the

## f. ITT Description
TOOL SUMMARY: INDICATOR TRACKING TABLE INSTRUCTIONS
Purpose | The ITT is a tool that is used as a tracking mechanism for all project indicators.
§ It requires setting targets for indicators on quarterly, annual, and life project timeframes
§ It documents baseline data for each indicator
§ It is normally developed after the M&E Plan Matrix has been completed and after the baseline data has been collected
§ It is a key project management tool that is closely linked to, and included in, project reports.
Information Sources | 1. Initial Assessment
2. Logframe
3. Project Proposal
4. Baseline
5. M&E Plan Matrix
Who | The ITT should be completed by the partner.
When | The ITT is a sub-tool of the Detailed M&E Plan and should therefore be completed according to the timeframe set out for the completion of the Detailed M&E Plan.
Recommendations | § Every project should have an ITT
§ The ITT should be updated with actual data for every reporting period. The ITT should be updated before beginning the narrative Project Progress Report.
o The ITT is a very useful management tool and is most effective when used on a quarterly basis. Use on a quarterly basis provides project managers with more regular data and can help in making timely adjustments and improvements to the project.
o If the required reporting period is semiannually, it is suggested that the ITT be completed on a quarterly basis, but that the analysis included in the Project Progress Report focus on progress for the entire six month period.
§ Targets can be revised, but there should be clear and convincing reasoning behind the revision. Indicator target revisions are not common and should be done only when there has been a major change to the scope or context of the project.
o For restricted projects, consult with the LWR Grants Manager before revising indicator targets
o For EDF projects, coordinate with the Program Associate before revising indicator targets
o If approval is given to revise indicator targets:
- Highlight revised targets in progress reports and provide clear and specific reasoning for the revisions
- Ensure that new targets are updated in the ITT and that all subsequent quarterly targets and annual and life of project targets reflect the revision
- Target revisions should also be communicated clearly to the donor
§ The “Status” column in the ITT can indicate the date the indicator data is expected to start and end, if it will only be collected at baseline and endline, if it is completed, or if it is ongoing. The “Status” column is NOT to be used to provide any narrative explanation about the indicator. This should be done in the Project Progress Report.
Tips* | § Baseline data is sometimes not yet available within the first 60 days of the project
o Complete targets based on best estimates and revise them as soon as the baseline data is available
§ Not meeting a target should be viewed as a learning experience, not as a failure.
o Discussions about why actual data is over or under a target is important
o Set ambitious targets, but also make them realistic by linking them as closely as possible to the project’s detailed implementation plan
§ Use the ITT as a key analysis and reporting tool
o Analyze why or why not targets were met to help you understand what adjustments to the project’s implementation should be made
§ Key findings from the analysis becomes central information for project reports, and can be shared with all relevant stakeholders
§ Indicators do not need to capture everything in a project, but only what is necessary and sufficient for monitoring and evaluation.
§ Counting myriad activities or outputs is useful for project management but does not show the project’s impact. For measuring project effects, it is preferable to select a few key output indicators and focus on outcome and impact indicators whenever possible.
§ Indicators need to be specific so that they can be readily measured.
o For example, it is better to ask how many children under age 5 slept under an insecticide-treated bednet the previous night than to inquire generally whether the household practices protective measures against malaria.
§ Complex information can be time-consuming, expensive, and difficult for local staff to understand, summarize, analyze, and work with. Keep it simple, clear, and concise.
*The final 5 tips were borrow directly from McMillan, D., Willard, A. 2004. “Preparing for an Evaluation Guidelines and Tools for Pre-Evaluation Planning.” Catholic Relief Services, Baltimore, MD, American Red Cross, Washington DC. P. 9

## g. ITT "Project Name" Year 1
LUTHERAN WORLD RELIEF INDICATOR TRACKING TABLE | [16 empty] | Project Beneficiaries
Project Name: | [17 empty] | Female | Male | Total
Report Period: |  |  | Partner: | [6 empty] | Project Year | [6 empty] | Direct |  |  | 0
Identifier: |  |  | Project Location: | [6 empty] | Project Start Date: | [6 empty] | Indirect |  |  | 0
Project Sector(s): | [9 empty] | Project End Date: | [6 empty] | Total | 0 | 0 | 0
RESULTS | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target | Project Component | Status
| Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
GOAL:
OUTCOME 1:
Indicator 1.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 1.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 1.1:
Indicator 1.1.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 1.1.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 1.2:
Indicator 1.2.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 1.2.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTCOME 2:
Indicator 2.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indciator 2.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 2.1:
Indicator 2.1.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 2.1.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 2. 2:
Indicator 2.2.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 2.2.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTCOME 3:
Indicator 3.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indciator 3.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 3.1:
Indicator 3.1.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 3.1.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 3. 2:
Indicator 3.2.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 3.2.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTCOME 4:
Indicator 4.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indciator 4.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 4.1:
Indicator 4.1.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 4.1.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 4.2:
Indicator 4.2.a: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 4.2.b: | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Note on Z7: The “Status” column in the ITT can indicate the date the indicator data is expected to start and end, if it will only be collected at baseline and endline, if it is completed, or if it is ongoing. The “Status” column is NOT to be used to provide any narrative explanation about the indicator. This should be done in the Project Progress Report.

## h. ATT Description
TOOL SUMMARY: ACTIVITY TRACKING TABLE INSTRUCTIONS
Purpose | The Activity Tracking Table is a complimentary tool to the Indicator Tracking Table. It allows activities to be tracked in a summary manner and in a separate tab. This helps show project progress towards achieving the project’s outputs without complicating the ITT.
§ The Activity Progress Summary row in the ATT, which sums up the progress on all activities linked to an Output, is linked to the Activity Progress Summary row in the ITT.
§ The ATT is a tool that is used in assisting the project team, the LWR PM, and LWR HQ track progress on the completion of planned activities. The ATT elaborates on the general Project Work Plan contained in the Project Design Book by listing all project activities and the estimated targets for each reporting period.
Information Sources | 1. Logframe
2. Project Proposal
3. M&E Plan Matrix
4. Indicator Tracking Table
Who | The ATT should be completed and updated by the partner, reviewed by the LWR PM, and included in each Project Progress Report.
When | The ATT is a sub-tool of the Detailed M&E Plan and should therefore be completed according to the timeframe set out for the completion of the Detailed M&E Plan.
Recommendations | The ATT is linked to the ITT and is used to track project progress. It therefore has similar recommendations as the ITT.
§ The completion of activities tells us little about changes in development conditions or in the lives of people. It is the results of these activities that are significant. Nevertheless, tracking the completion of planned activities is a very important management tool. LWR therefore encourages the use of the Activity Tracking Table instead of including the tracking of activities in the ITT or in a logframe template.
§ Every project should have an ATT
§ The ATT should be updated with actual data for every reporting period. The ATT should be updated before beginning the narrative Project Progress Report.
o The ATT is a key management tool and is most effective when used on a quarterly basis. Use on a quarterly basis provides project managers with more regular data and can help in making timely adjustments and improvements to the project.
o If the required reporting period is semiannually, it is suggested that the ATT be completed on a quarterly basis, but that the analysis included in the Project Progress Report focus on progress for the entire six month period.
§ Setting targets for the number of activities to be completed in a reporting period is a way to ensure that all activities are completed by the end of the project. LWR understand that many factors affect the completion of activities according to plan. Nevertheless, the project should strive to complete activities as planned, which is most easily tracked by tracking the completion of activities according to targets.
o Section 3.1.a. of the Project Progress Report is dedicated to an analysis of the progress towards meeting activity targets. This will allow the project team to explain in more detail the simplified quantitative activity tracking of the ATT.
Tips | § Not meeting a target should be viewed as a learning experience, not as a failure.
o Discussions about why actual data is over or under a target is important
o Set ambitious targets, but also make them realistic by linking them as closely as possible to the project’s detailed implementation plan
§ Use the ATT as a key analysis and reporting tool
o Analyze why or why not activity targets were met, analyze them in the context of how they relate to meeting impact indicator targets, and use the results to help you determine any adjustments to the project’s implementation plan that should be made.
o Key findings from the analysis becomes central information for project reports, and can be shared with all relevant stakeholders
§ Reporting detailed information about sub-tasks to complete activities can be time-consuming and confusing for report reviewers at the regional and Head Quarters level. Keep it simple, clear, and concise.

## i. ATT "Project Name" Year 1
LUTHERAN WORLD RELIEF ACTIVITY TRACKING TABLE
Project Name:
Report Period: | Partner: | [5 empty] | Project Year
Identifier: | Project Location: | [5 empty] | Project Start Date:
Project Sector(s): | [6 empty] | Project End Date:
| Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target | Project Component | Status
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 1.1:
ACTIVITY 1.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.1. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 1.2:
ACTIVITY 1.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.2. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 2.1:
ACTIVITY 2.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.1. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 2. 2:
ACTIVITY 2.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.2. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 3.1:
ACTIVITY 3.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.1. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 3. 2:
ACTIVITY 3.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.2. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 4.1:
ACTIVITY 4.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.1. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 4.2:
ACTIVITY 4.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.2. B |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA