## Design Workbook Instructions
TOOL SUMMARY: PROJECT DESIGN WORKBOOK INSTRUCTIONS
Purpose | The purpose of the Project Design Workbook is to consolidate and link in ONE document the outputs from all the project design tools. The tabs include:
1. Problem Tree Analysis Documentation
2. Problem to Objectives
3. Results Framework
4. Logframe
5. Work Plan
Information Sources | 1. Needs Assessment
2. Problem Tree Analysis
3. Objective Tree Analysis
4. Results Framework
Who | The project design should be coordinated/facilitated by one person who leads the entire design process. For EDF projects this will often be the LWR Program Manager, but can be a representative from the partner or even the LWR Country Director. The factors to consider when determining the lead for this process is his/her familiarity with target population, familiarity with the results from the needs assessment, and experience in using the tools described in the Purpose.
For restricted project proposals over the NBD threshold ($500,000) the person responsible for the completion of the Project Design Workbook is the Technical Design Facilitator, who is selected during the Proposal Kickoff Meeting by the Decision Maker and the Deputy Director for NBD .The Technical Design Facilitator:
Leads the technical design workshop, including problem analysis and logical framework development with LWR, partners and technical experts.
Ensures that each tab in the Project Design Workbook contains the results from the project design tools adhere to donor guidance and are recorded clearly.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual.
When | Each template of The Project Design Workbook should be filled with the final results from the project design tools.
Recommendations | § It is recommended that all projects complete the Project Design Workbook so that its entire design is captured in one document and that the results located in each tab are linked. The completion of this document forms the foundation of the technical and cost proposals, as it outlines the entire project design.
o Completion of the template is encouraged for all project proposals and is required for proposals over the NBD threshold ($500,000).
§ The Work Plan is a supplemental document often required for proposal development. The Work Plan outlines when each proposed project activity, linked to a specific Output, will take place over the life of the project. Some Outputs targets may be completed before the end of the project while others will have targets that are not met until the end of the project. It is important to document this as it helps in monitoring and tracking spending, schedules and budgets. Included in the Work Plan is a guideline for tracking who is responsible for the completion of specific activities. In some cases, this may be an individual, but in larger consortiums, this may be a place to indicate that a proposed partner is responsible for completion of a specific result.
Tips | § The final three templates (results framework, logframe, work plan) of the Project Design Workbook are designed to be used together and are linked, so when you enter information into the Results Framework, it automatically fills in details in the Logical Framework, and Work Plan. This ensures that the objective statements are consistent throughout the document. If edits are made to the objective statements, only make changes in the Results Framework.
o Because the Results Framework, Evidence for Cause, Logframe, and Work Plan are linked, it is very important not to modify the formulas in the objective statement columns of the Evidence for Cause, Logframe and Work Plan tabs. If you have any questions about modifying these templates, please contact the M&E Unit or the NBD Unit for technical support.
§ Working in Word format, in particular for tools that require lots of narrative, is often easier than working in Excel. Therefore, the Word format can be used for the first drafts of each tool in the Project Design Workbook and once the final draft has been completed the results copied and transferred to this Excel template.
§ The Problem Tree Documentation is NOT linked to the other tabs. The final results from these activities simply need to be documented.
o If the Word template is used for these two tools, it must be transferred to the Project Design Workbook once completed. To do so, copy the whole graphic and paste it into the Project Design Workbook using the “Paste Special” function and paste it as a “Picture (PNG)”
KEY: Any method or program can be used to document the results of the Problem Tree in the Project Design Workbook. What is important is that the results are documented.

## a. Problem Analysis Summary
TOOL SUMMARY: PROBLEM TREE
Purpose | The Problem Tree is a method for conducting a problem analysis. The purpose of a problem analysis is to study of one or more problems (identified during the assessment stage), to identify the causes and decide whether and how to address them.
§ The Problem Tree method is used to structure, summarize and organize the initial findings of the needs assessment. It takes the form of a tree which helps visualize the overall situation with the causes being the roots of the tree, the problem as the trunk, and the effects as the branches.
o Merely listing and ranking problems does not provide for a sufficiently deep analysis of the situation.
Information Sources | 1. IFRC Project Planning Guidance Manual: 4.1.4: Problem analysis using the “problem tree” tool (P. 21-22)
2. IFRC Project Planning Guidance Manual: Annex 1: How to create a problem tree (P. 51-53)
3. Initial situation/needs assessment
4. Other needs assessment data
5. Project team experience
Who | The problem analysis using the Problem Tree method should be coordinated/facilitated by one person who leads the entire process. For UNRESTRICTED projects this will often be the LWR Program Manager, but can be a representative from the partner or even the LWR Country Director.
§ The factors to consider when determining the lead for this process is his/her familiarity with target population, familiarity with the results from the needs assessment, and experience in using the Problem Tree method.
§ Doing the Problem Tree with participation of representatives of the target population is ideal. The target population is most familiar with the problems and the context.
For RESTRICTED projects the person responsible for the completion of the Problem Tree as well as the remaining aspects of the project design is the Technical Design Coordinator, who is selected during the Proposal Kickoff Meeting. The Technical Design Coordinator:
§ Leads the technical design workshop with participation from LWR, partners and technical experts. The technical design workshop covers the problem analysis (Problem Tree), development of possible solutions to the problem by creating expected results (Objectives Tree) and confirming the logic of the selected results (Results Framework and Logical Framework)
§ Writes sections including: Project Design Workbook, which may include Problems to Objectives, Results Framework, Logframe, Implementation Plan and/or M&E Plan Matrix depending on donor guidance.
For proposals under the threshold ($500,000), the Decision Maker will identify the Technical Design Facilitator. For proposals over the threshold, the Decision Maker and the Deputy Director for NBD will select the Technical Design Facilitator.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual.
When | The Problem Tree method is used after the needs assessment and before starting work on the Objectives Tree.
Recommendations | § The Problem Tree method is not required, but some form of problem analysis should be completed for all projects.
o The Problem Tree method is a very effective tool and LWR recommends that it be used as the primary problem analysis method. LWR’s past Problem Analysis box can also be used to document the results, but it is recommended that the concept behind the Problem Tree method form the foundation for analysis.
§ For some RESTRICTED proposals the donor may specify the problem statement or the causes, or both.
o In cases where the problem statement is provided, then the problem analysis should focus on determining only the causes to that problem. The analysis of the causes should still be based on what is known about the target area/population as a result of the needs assessment.
o If both the problem statement and the causes are specified by the donor, the problem analysis is NOT required. The design team can move directly to conducting the Objectives Tree analysis and completing the Problem to Objectives tab.
§ It is recommended that the problem statement and each cause identified be linked to data that verifies its existence in the target population and the degree to which it affects the target population.
o For example, if the project goal is "improved agricultural productivity", the corresponding description of the cause would be "poor agricultural productivity in the target area." The degree to which the cause affects the target population would be represented by specific data would verify the “how poor” the agricultural productivity is in the area (i.e. 50% reduction from average in the past year).
o The documented source may be a LWR needs assessment, peer agency needs assessment, government report, agency report, or other published document
o This source is documented in the Project Design Workbook in the Problem to Objectives tab.
§ The process is as important as the product. The exercise should be treated as a learning experience and an opportunity for different views and interests to be expressed.
§ If necessary, the different aspects of a problem area can be further elaborated through focus groups or interviews.
§ The Word template provided is a typical graphical presentation of a Problem Tree. The graphic can be manipulated (size and number of boxes) to reflect the results of the Problem Tree analysis, which is often completed with sticky notes and flip chart.
o If the Word template is used it must be transferred to the Project Design Workbook once completed. To do so, copy the whole graphic and paste it into the Project Design Workbook using the “Paste Special” function and paste it as a “Picture (PNG)”
o An alternative option is to take a photo of the results and paste it into the Project Design Workbook.
KEY: Any method or program can be used to document the results of the Problem Tree in the Project Design Workbook. What is important is that the results are documented.
Tips | § Completing the problem analysis (Problem Tree) can be complex, therefore experience in facilitating the use of the Problem Tree method and familiarity with the local context is of utmost importance when selecting a lead coordinator/facilitator.
§ Does each cause-effect link (illustrated by arrows) make sense? Is each link plausible? Why or why not?
§ How well have the causes gone down to the roots? Are there any unidentified root causes?
§ What appears to be the relative contribution of each causal stream (causes linked by arrows leading to the core problem statement) to the problem? Do some causes appear more than once? Why is this? Which causes show significant influence?
§ Depending on the depth of analysis, the lowest cause identified in the Problem Tree can relate directly to chosen activities.

## b. Problem Tree Documentation
Instructions: The easiest way to document the Problem Tree analysis is to use the “Snipping Tool” which is Microsoft tool found in the Start Menu: All Programs – Accessories – Snipping Tool. Select and copy the whole graphic and paste it into the Project Design Workbook in the Problem Tree Documentation tab. The Snipping tool can be used to copy and paste from any electronic medium, including websites, Microsoft office applications, etc.
KEY: Any method or program can be used to document the results of the Problem Tree analysis in the Project Design Workbook. What is important is that the results are documented and can be clearly read.
Below is an example of a Word template pasted in the tab using the Snipping tool. Simply delete this example and paste your finalized Problem Tree analysis results when it is completed.

## c. Objective Tree Summary
TOOL SUMMARY: OBJECTIVES TREE
Purpose | The purpose of the Objective Tree is to represent ALL possible objectives/results that the project has identified to solve the problem identified in the Problem Tree analysis. It is a tool to aid analysis and the presentation of solutions. Its main strength is that it keeps the analysis of potential project objectives/results firmly rooted in addressing a range of clearly identified priority problems. Whereas problems analysis seek to identify current negative conditions, objectives analysis aims to display all possible solutions and will form the foundation for the project’s specific strategies.
§ The Objectives Tree is the intermediate step between the Problem Tree and the Results Framework. The difference between the Objective Tree and the Results Framework is that The Results Framework shows the final results that the project has selected, leaving out those objectives that are not relevant or are too resource intensive.
§ Demonstrate and describe the situation in the future if all the identified problems were remedied
§ It identifies possible objectives (intended results) and verifies the hierarchy between them
§ It illustrate and verifies the causal (means-ends) relationships through a diagram
§ It establishes priorities by:
o assessing how realistic the achievement of some objectives may be and
o identifying additional means that may be required to achieve the intended results
Information Sources | 1. IFRC Project Planning Manual: 4.2 Development of objectives (P. 22-24)
2. IFRC Project Planning Manual: Annex 2: How to create and use an objectives tree (P. 54-56)
3. Problem Tree results
Who | The completion of the Objective Tree should be coordinated/facilitated by one person who leads the entire project design process. For UNRESTRICTED projects this will often be the LWR Program Manager, but can be a representative from the partner or even the LWR Country Director. The factors to consider when determining the lead for this process is his/her familiarity with target population, familiarity with the results from the needs assessment, and experience in using the Objective Tree method.
For RESTRICTED projects the person responsible for the completion of the Problem Tree as well as the remaining aspects of the project design is the Technical Design Coordinator, who is selected during the Proposal Kickoff Meeting. The Technical Design Coordinator:
§ Leads the technical design workshop with participation from LWR, partners and technical experts. The technical design workshop covers the problem analysis (Problem Tree), development of possible solutions to the problem by creating expected results (Problem to Objectives) and confirming the logic of the selected results ( Results Framework and Logical Framework)
§ Writes sections including: Project Design Workbook, which may include Problems to Objectives, Results Framework, Logframe, Implementation Plan and/or M&E Plan Matrix depending on donor guidance.
For proposals under the threshold ($500,000), the Decision Maker will identify the Technical Design Facilitator. For proposals over the threshold, the Decision Maker and the Deputy Director for NBD will select the Technical Design Facilitator.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual.
When | The Objective Tree tool is used after the Problem Tree is completed and is documented in the Problem to Objectives tab of the Project Design Workbook. The objective analysis using the Objective Tree is the intermediate step between the creation of the Problem Tree and the creation of the Results Framework.
Recommendations | 1. There may be some causes near the bottom of the tree that are very general. They cannot be turned into objectives that can easily be addressed by an intervention. Instead, they act as external factors that need to be considered and assessed to verify the feasibility of the intervention
2. Use the Problem to Objectives tab of the Project Design Workbook to document all the possible solutions (Goal, Outcomes, Outputs) to the problem and causes identified during the Problem Tree analysis. Use the Objective Tree Method to determine the final solution identified by the project. The Results Framework tab will document the final solution that is chosen.
Tips | § Are the positive statements and objectives clear?
§ Have they been put into a logical and reasonable order that shows means-to-ends logic?
§ Is there a need to add other objectives?
§ How do these objectives differ from the initial assessment of how the intervention should be designed?
[1] Borrowed directly from: IFRC (International Federation of the Red Cross and Red Crescent Societies). 2010. Project/ Program Planning Guidance Manual. Geneva. P. 23

## d. Problem to Objective Summary
TOOL SUMMARY: PROBLEMS TO OBJECTIVES
Purpose | The purpose of the Problems to Objectives tool is two-fold:
1. It documents the links between the problems/causes (from the Problem Tree analysis) and the source of evidence (citation) that confirms the existence and degree of each problem and cause.
a. Example: "reduced agricultural output in the priority action zone" is the problem and the evidence with citation could be “Agricultural output in the PAZ has decreased by 25% from 2011-2013 (Needs assessment section 2.1).”
2. It documents the links between the problems and causes which describe the negative condition in the target population, and positive conditions, or expected results (from the Objective Tree analysis) that the project seeks to achieve. These expected results are the inverse of the problem/cause and are written as objective statements (as described in the Logframe Cheat Sheet)
a. Example: "reduced agricultural output in the priority action zone" is the problem and the expected result is “The target beneficiaries in the PAZ have increased agricultural output.”
Information Sources | 1. Problem Tree Analysis results
2. Objective Tree Analysis results
3. Needs Assessments
4. Peer agency needs assessment
5. Government report
6. Agency report
7. Other published document
Who | The completion of the Problems to Objective tab should be coordinated/facilitated by one person who leads the entire project design process. For UNRESTRICTED projects this will often be the LWR Program Manager, but can be a representative from the partner or even the LWR Country Director.
For RESTRICTED projects the person responsible for the completion of the Problem Tree as well as the remaining aspects of the project design is the Technical Design Coordinator, who is selected during the Proposal Kickoff Meeting. The Technical Design Coordinator:
Leads the technical design workshop with participation from LWR, partners and technical experts. The technical design workshop covers the problem analysis (Problem Tree), development of possible solutions to the problem by creating expected results (Objectives Tree) and confirming the logic of the selected results (Results Framework and Logframe)
Writes sections including: Project Design Workbook, which may include Problem to Objectives, Results Framework, Logframe, Implementation Plan and/or M&E Plan Matrix depending on donor guidance.
For proposals under the threshold ($500,000), the Decision Maker will identify the Technical Design Facilitator. For proposals over the threshold, the Decision Maker and the Deputy Director for NBD will select the Technical Design Facilitator.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual.
When | § The Problem/Cause column is filled in with the final results from the Problem Tree analysis.
§ The Evidence of Problem/Cause with Citation column should be completed while the problems and causes are being identified and confirmed and entered into this column after they have been finalized.
§ The Objective Statement column can be filled in either after completing the Objective Tree analysis or after verifying the logic of the expected results in the Results Framework.
Recommendations | § There is no set point when this tool should be used. You will often have to move back and forth between this tool, the Problem Tree analysis and the Objective Tree analysis and the Results Framework in order to complete all of them and confirm the links between each tool.
§ If you know a problem or cause will NOT be included in the end project design, you do not have to complete this column for that Problem or Cause.
§ Sometimes the project team will simply know that a problem or cause exists from many years of interaction with the target population or zone.
o Nevertheless, it is a good exercise to reaffirm what is known by conducting a new needs assessment or undertaking a short investigation of relevant studies or government data for the area when proposing a new project.
Tips | § Double check that each objective statement is written according to the guidelines outlined in the Logframe Cheat Sheet.
§ Double check that each objective statement is the inverse of the problem or cause to which it is linked.
§ Make sure to document clearly the results of your needs assessment and file any studies or government data about a target population or region so that it is easily available to reference during the design phase of the project.
§ Use this as a tool to help ensure a strong project design, but don’t let the template hinder the development of the design. The concept is important, you can use any method that works best and simply document the results in this document.

## e. Problems to Objectives
Explanation | The PROBLEM/CAUSE column where the problems and causes from the Probelm Tree analysis are entered. Remember, the problems and causes are the actual situation in the target area expressed as the negative condition. | The EVIDENCE FOR PROBLEM/CAUSE W/CITATION column is a way to document the source of the evidence for each problem or cause. It helps ensure that the problems and causes identified in the project design are based on actual or observed situations. It is a way to document what is found in the needs assessment, but can also come from peer agency needs assessment, government report, agency report, or other published document. The document or source of the evidence for each problem/cause should be place which is placed in parenthesis behind the evidence. For example, if the Problem is "poor agricultural productivity in the priority action zone" then the evidence with citation could be “Agricultural output in the PAZ has decreased by 25% from 2011-2013 (Needs assessment section 2.1).” The citation helps document key information and can also assists in setting indicator or beneficiary targets. |  | The OBJECTIVE STATEMENT column is where the project's objectives are documented. Having this column on the same page as the PROBLEM/CAUSE helps ensure that the proposed objective responds to the problems/causes identified during the assessment stage. The objectives statements are the opposite of negative condition identified in the Problem Tree analysis. They are written as the positive condition and as if the result has already been acheived. The Objective Tree Analysis Tool Summary, as well as the guidance in the sections related to the objective analysis in the IFRC Project Planning Guidance, can assist in selecting the most appropriate objectives for the context of the project. The Results Framework can then be used to verify the logic between the selected Goal, Outcomes, and Outputs
Project Title:
# | PROBLEM/CAUSE | EVIDENCE FOR PROBLEM-CAUSE W/ CITATION | # | OBJECTIVE STATEMENT
Problem 1 |  |  | GOAL:
Cause 1 |  |  | Outcome 1
Cause 1.2 |  |  | Output 1.1
Cause 1.3 |  |  | Output 1.2
Cause 1.4 |  |  | Output 1.3
Cause 1.5 |  |  | Output 1.4
Cause 1.6 |  |  | Output 1.5
Cause 2 |  |  | Outcome 2
Cause 2.1 |  |  | Output 2.1
Cause 2.2 |  |  | Output 2.2
Cause 2.3 |  |  | Output 2.3
Cause 2.4 |  |  | Output 2.4
Cause 2.5 |  |  | Output 2.5
Cause 3 |  |  | Outcome 3
Cause 3.1 |  |  | Output 3.1
Cause 3.2 |  |  | Output 3.2
Cause 3.3 |  |  | Output 3.3
Cause 3.4 |  |  | Output 3.4
Cause 3.5 |  |  | Output 3.5
Cause 4 |  |  | Outcome 4
Cause 4.1 |  |  | Output 4.1
Cause 4.2 |  |  | Output 4.2
Cause 4.3 |  |  | Output 4.3
Cause 4.4 |  |  | Output 4.4
Cause 4.5 |  |  | Output 4.5
Cause 5 |  |  | Outcome 5
Cause 5.1 |  |  | Output 5.1
Cause 5.2 |  |  | Output 5.2
Cause 5.3 |  |  | Output 5.3
Cause 5.4 |  |  | Output 5.4
Cause 5.5 |  |  | Output 5.5

## f. Results Framework Summary
TOOL SUMMARY: RESULTS FRAMEWORK
Purpose | The purpose of the Results Framework is to verify the logic between the proposed project results using “if-then” logic and to visually present the project’s final strategy for achieving its goal.
§ It is a representation of the finalized Objectives Tree where the final solutions (groups of objectives) are selected and the objectives that cannot be addressed by the project are discarded. It is laid out in graphic form based on a hierarchy of results.
A Results Framework includes the overall expected result of the project (goal) and the additional intermediate results along the results hierarchy (activities, outputs, outcomes) necessary to achieve it.
The framework also conveys the development hypothesis implicit in the strategy and the cause-and-effect linkages between the intermediate results and the goal.
Information Sources | 1. Problem Tree results
2. Objective Tree results
3. USAID Tips: BUILDING A RESULTS FRAMEWORK
4. Logframe Cheat Sheet
Who | The completion of the Results Framework should be coordinated/facilitated by one person who leads the entire project design process. For UNRESTRICTED projects this will often be the LWR Program Manager, but can be a representative from the partner or even the LWR Country Director.
For RESTRICTED projects the person responsible for the completion of the Problem Tree as well as the remaining aspects of the project design is the Technical Design Coordinator, who is selected during the Proposal Kickoff Meeting. The Technical Design Coordinator:
§ Leads the technical design workshop with participation from LWR, partners and technical experts. The technical design workshop covers the problem analysis (Problem Tree), development of possible solutions to the problem by creating expected results (Objectives Tree) and confirming the logic of the selected results (Results Framework and Logical Framework)
§ Writes sections including: Project Design Workbook, which may include Problem to Objectives, Results Framework, LogFrame, Implementation Plan and/or M&E Plan Matrix depending on donor guidance.
For proposals under the threshold ($500,000), the Decision Maker will identify the Technical Design Facilitator. For proposals over the threshold, the Decision Maker and the Deputy Director for NBD will select the Technical Design Facilitator.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual.
When | The Results Framework is completed after completing the Objective Tree and provides the content, the project results, for the first column of the Logframe.
Recommendations | § It is recommended that Results Framework be completed for every project.
§ LWR recommends using only 4 levels of results (Goal, Outcome, Output, Activities), but recognizes that some projects may require an Intermediate Result, in particular projects with large scopes. Intermediate Results would fall between the Outputs and Outcomes and would follow the same formula for writing the objective statement as the Outputs and Outcomes. Outputs (or multiple Outputs) would lead to an Intermediate Result and Intermediate Results (or multiple Intermediate Results) would lead to the Outcome.
o Intermediate Results are normally identified as necessary during the development of the Results Framework and reflect problem analysis results that have more than 3 levels of causes. There must be a continued strong “if-then” logic between the Intermediate Results and the Outcomes and Outputs linked to it.
§ The completion of a Results Framework is required for all project proposals over $500,000
§ The project design team can use the Word format below to create the Results Framework.
o The graphic can be manipulated (size and number of boxes) to reflect the number of objective statements (Goals, Outcomes, Outputs) for the project.
o If the Word template is used it must be transferred to the Project Design Workbook under the Results Framework tab once completed.
Tips | § Identify different ways to involve stakeholders in project review and adaptation. Build in flexibility to respond to unplanned opportunities.
§ The Results Framework is normally developed from the Goal down to the Activities, but you might not work down from Goal to Activities in a perfectly linear fashion. It may be easier to skip around among different levels to some extent. That is fine, because in fact, it is the way creating a logframe sometimes proceeds!
§ Unlike other result statements, Goals are usually rather general and abstract, and they describe a desired state that occurs beyond the life of the project.
§ Focus especially on establishing clear Outcomes since these essentially represent the purpose of the project investment. It also helps to ensure that the focus of the design of the project is on the ultimate impacts the project seeks to achieve rather than focusing on activities.
§ Focus on clear Outputs since these are the deliverables that underpin behavioral change at Outcome level
o Be clear in your Outputs statements about what changes you expect to see among those you are targeting.
§ Ensure the logic between each level of your objectives by using the “if – and- then” test.
o Example: IF…the partner conducts disaster management trainings (activity)…AND…the communities don’t have any unplanned demands on their time (assumption)…THEN…communities have improved awareness of measures to prepare for and respond to disasters (output).
§ Do not over-specify activities. This can cause you to spend less time on the more important elements of the logframe (Outcome and Output level objectives).
o Activities should be chosen based on their ability to most effectively address the causes of the problem identified in the problem analysis.
§ It is always helpful to define the duration of your proposed project. This will certainly help you to be realistic in finalizing your outcomes, i.e. what is achievable by the end of project.
§ There can be more Outputs and Outcomes than outlined below. Add or subtract more boxes as needed.
§ It is important to ensure that the project’s goal is oriented towards more high level development results, as outlined in the Logframe Cheat Sheet.

## g. Results Framework
The following 3 templates (Results Framework, Logframe, Work Plan) are designed to be used together and some cells are linked. When you enter information into the Results Framework, it automatically fills in details in the Logical Framework and Work Plan. This ensures that the objectives statements are consistent throughout the document. If edits are made to the objective statements, only make changes in the Results Framework. Because the Results Framework, LogFrame, and WorkPlan are linked, it is very important to NOT modify the formulas in the objective statement columns of the Evidence for Cause, Logframe and Work Plan tabs. If you have any questions about modifing these templates, please contact the M&E Unit or the NBD Unit for technical support.
Project Title
GOAL:
Outcome |  | Outcome |  | Outcome |  | Outcome |  | Outcome
1 |  | 2 |  | 3 |  | 4 |  | 5
| Output |  | Output |  | Output |  | Output |  | Output
| 1.1 |  | 2.1 |  | 3.1 |  | 4.1 |  | 5.1
| 1.2 |  | 2.2 |  | 3.2 |  | 4.2 |  | 5.2
| 1.3 |  | 2.3 |  | 3.3 |  | 4.3 |  | 5.3
| 1.4 |  | 2.4 |  | 3.4 |  | 4.4 |  | 5.4
| 1.5 |  | 2.5 |  | 3.5 |  | 4.5 |  | 5.5

## h. Logframe Summary
TOOL SUMMARY: LOGFRAME TEMPLATE-DEFINITIONS-EXAMPLE
Purpose | The purpose of the Logframe is to SUMMARIZE the entirety of the project’s logic by outlining it’s expected results (Goal, Outcome, Output, Activities), how the achievement of the results will be measured (indicators), how the data to measure the results will be collected and verified (Means of Verification), and the assumptions made about the logic between each level of the expected results (Assumptions).
§ The logframe matrix consists of a table with four rows and four columns, in which the key aspects of a project are summarized. It sets out a logical sequence of cause-effect relationships based on the results chain/objectives hierarchy.
The Logframe does not show every detail of a project. Further details, such as the proposal, budget, Detailed M&E Plan, and activity schedule, can be provided in other documents that accompany the Logframe,
All additional project documents should refer to and be developed based upon the Logframe.
It is a living document, which should be consulted and altered throughout the intervention’s life cycle.
Information Sources | 1. Results Framework
2. Project Design Workbook
3. Detailed M&E Plan
4. Project indicators or standard indicator lists
5. External or contextual information or data that can help with defining the project’s assumptions
Who | The development of the project’s Logframe is one of the most important components of the project’s design. Many people will be involved in developing the Logframe, but one person should be assigned responsibility during the proposal kickoff meeting to manage feedback, do version control, and ensure that the final draft is completed on time. For UNRESTRICTED projects this will often be the LWR Program Manager, but can be a representative from the partner or even the LWR Country Director.
Identify different ways to involve stakeholders in project review and adaptation. Build in flexibility to respond to unplanned opportunities.
It is good to have one reviewer of the Logframe who is not part of the core proposal development team. An outside perspective can help identify gaps in logic or missing details resulting from the familiarity of the proposal development team with the project proposal.
For RESTRICTED projects the person responsible for the completion of all aspects of the project design is the Technical Design Coordinator, who is selected during the Proposal Kickoff Meeting. The Technical Design Coordinator:
Leads the technical design workshop with LWR, partners and technical experts.
Writes sections including: Project Design Book, which may include Problem to Objectives, Results Framework, Logframe, Implementation Plan and/or Performance Monitoring Plan (PMP) depending on donor guidance.
For proposals under the threshold ($500,000), the Decision Maker will identify the Technical Design Facilitator. For proposals over the threshold, the Decision Maker and the Deputy Director for NBD will select the Technical Design Facilitator.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual.
When | The Logframe is developed after the Results Framework is completed. The results chain/objectives hierarchy developed in the Results Framework is transferred to the first column of the Logframe and then work begins on completing the remaining three columns (indicators, means of verification, assumptions). The completed Logframe will be the foundation for completing the M&E Plan Matrix in the DMEL Process of Create detailed M&E plan.
§ The example below, as well as the Logframe Cheat Sheet, provide concrete examples and guidance on completing a quality Logframe
Recommendations | 1. The logframe template that is included in this process is LWR’s new standard
§ This template should be used for all UNRESTRICTED funded projects
2. This template is the most widely accepted template by major donors, with the main variations being the different terminology for objectives/results
§ The terms used in the logical framework vary across organizations and amongst donors.
§ For unrestricted funded projects, the terminology used in the LWR logframe should be followed.
· The IFRC Project Planning Guidance Manual has an example of a Logframe on page 40, but uses slightly different terminology than what is proposed in this example and LWR’s Logframe Cheat Sheet. IFRC’s example can be used as an additional reference, but LWR’s terminology should be used as the standard.
§ For donor funded projects, the terminology used by the donor should be employed when creating the Logframe. Please refer to the Logframe Master Translator to understand more clearly how donor terms match with LWR standard terms.
2. The blank Word logframe template below can be used when brainstorming and editing the content of the logframe. Once a draft of the logframe is completed the content should be transferred to the Project Design Workbook by copying the content into the corresponding cells in the Logframe tab.
3. Activities can be included in the Logframe in order to show the link between the proposed activities and the Output. Nevertheless, projects can contain vast amounts of activities and detailing information in each column of the Logframe for every activity can make it difficult to clearly see the logical sequence of cause-effect relationships of the project. It is therefore recommended to list the project’s major activities in the Logframe, but that the details concerning indicators and means of verification be defined in the project’s Work Plan.
4. In the example you will see that for Outcome 1, targets for the INDICATORS are placed in parenthesis after the indicator. This method can be used if indicator targets are known at this stage (primarily from reliable data obtained during the needs assessment), but often indicator targets are not finalized until baseline data has been collected. Finalized indicator targets should be documented in the projects Indicator Tracking Table which is developed during the DMEL Process: Develop detailed M&E plan.
5. SMART Criteria:
§ It is recommended that objective statements in the Logframe are NOT written using SMART criteria.
o Nevertheless, SMART objective statements can sometimes be used effectively within project proposals to show all the details of the expected result in one statement.
§ SMART criteria should be applied to indicators, not objective statements. (reference P. 37 of IFRC Project Planning Guidance Manual for further information on SMART criteria)
§ Follow the instructions and examples for writing indicators found in the Logframe Cheat Sheet
§ Additional SMART criteria for each indicator is detailed during completion of the M&E Plan Matrix
Tips | 1. Identify different ways to involve stakeholders in project review and adaptation. Build in flexibility to respond to unplanned opportunities.
2. You might not work down from Goal to Activities in a perfectly linear fashion. It may be easier to skip around among different levels to some extent. That is fine, because in fact, it is the way creating a logframe sometimes proceeds!
3. Unlike other result statements, Goals are usually rather general and abstract, and they describe a desired state that occurs beyond the life of the project.
4. Focus especially on establishing clear Outcomes since these essentially represent the purpose of the project investment.
5. Focus on clear Outputs since these are the deliverables that underpin behavioral change at Outcome level
§ Be clear in your Outputs statements about what changes you expect to see among those you are targeting.
6. Ensure the logic between each level of your objectives by using the “if – and- then” test.
§ Example: IF…the partner conducts disaster management trainings (activity)…AND…the communities don’t have any unplanned demands on their time (assumption)…THEN…communities have improved awareness of measures to prepare for and respond to disasters (output).
7. Do not over-specify activities. This can cause you to spend less time on the more important elements of the logframe (Outcome and Output level objectives).
8. It is always helpful to define the duration of your proposed project. This will certainly help you to be realistic in finalizing your outcomes, i.e. what is achievable by the end of project.
9. It is important to monitor critical assumptions during implementation. Your M&E Plan should include this responsibility.
10. You do not need to have an assumption at each level in the final draft of your logframe; this is not an exercise to fill in all of the boxes!
11. Always be realistic in setting targets. Support your arguments for the ones you do set (ideally from benchmark data), and also for the ones you can’t!
12. How many indicators? Stick to the “less is more” principle.

## i. LogFrame
Project Title
|  | PROBLEM/CAUSE | EVIDENCE OF PROBLEM-CAUSE WITH CITATION | OBJECTIVE STATEMENT | OBJECTIVELY VERIFIABLE INDICATOR | MEANS OF VERIFICATION | RISK AND ASSUMPTION
GOAL: |  | 0 | 0 | 0
Outcome | 1 | 0 | 0 | 0
Output | 1.1 | 0 | 0 | 0
Activity | 1.1.A.
Activity | 1.1.B.
Activity | 1.1.C.
Output | 1.2 | 0 | 0 | 0
Activity | 1.2.A.
Activity | 1.2.B.
Activity | 1.2.C.
Output | 1.3 | 0 | 0 | 0
Activity | 1.3.A.
Activity | 1.3.B.
Activity | 1.3.C.
Output | 1.4 | 0 | 0 | 0
Activity | 1.4.A.
Activity | 1.4.B.
Activity | 1.4.C.
Output | 1.5 | 0 | 0 | 0
Activity | 1.5.A.
Activity | 1.5.B.
Activity | 1.5.C.
Outcome | 2 | 0 | 0 | 0
Output | 2.1 | 0 | 0 | 0
Activity | 2.1.A.
Activity | 2.1.B.
Activity | 2.1.C.
Output | 2.2 | 0 | 0 | 0
Activity | 2.2.A.
Activity | 2.2.B.
Activity | 2.2.C.
Output | 2.3 | 0 | 0 | 0
Activity | 2.3.A.
Activity | 2.3.B.
Activity | 2.3.C.
Output | 2.4 | 0 | 0 | 0
Activity | 2.4.A.
Activity | 2.4.B.
Activity | 2.4.C.
Output | 2.5 | 0 | 0 | 0
Activity | 2.5.A.
Activity | 2.5.B.
Activity | 2.5.C.
Outcome | 3 | 0 | 0 | 0
Output | 3.1 | 0 | 0 | 0
Activity | 3.1.A.
Activity | 3.1.B.
Activity | 3.1.C.
Output | 3.2 | 0 | 0 | 0
Activity | 3.2.A.
Activity | 3.2.B.
Activity | 3.2.C.
Output | 3.3 | 0 | 0 | 0
Activity | 3.3.A.
Activity | 3.3.B.
Activity | 3.3.C.
Output | 3.4 | 0 | 0 | 0
Activity | 3.4.A.
Activity | 3.4.B.
Activity | 3.4.C.
Output | 3.5 | 0 | 0 | 0
Activity | 3.5.A.
Activity | 3.5.B.
Activity | 3.5.C.
Outcome | 4 | 0 | 0 | 0
Output | 4.1 | 0 | 0 | 0
Activity | 4.1.A.
Activity | 4.1.B.
Activity | 4.1.C.
Output | 4.2 | 0 | 0 | 0
Activity | 4.2.A.
Activity | 4.2.B.
Activity | 4.2.C.
Output | 4.3 | 0 | 0 | 0
Activity | 4.3.A.
Activity | 4.3.B.
Activity | 4.3.C.
Output | 4.4 | 0 | 0 | 0
Activity | 4.4.A.
Activity | 4.4.B.
Activity | 4.4.C.
Output | 4.5 | 0 | 0 | 0
Activity | 4.5.A.
Activity | 4.5.B.
Activity | 4.5.C.
Outcome | 5 | 0 | 0 | 0
Output | 5.1 | 0 | 0 | 0
Activity | 5.1.A.
Activity | 5.1.B.
Activity | 5.1.C.
Output | 5.2 | 0 | 0 | 0
Activity | 5.2.A.
Activity | 5.2.B.
Activity | 5.2.C.
Output | 5.3 | 0 | 0 | 0
Activity | 5.3.A.
Activity | 5.3.B.
Activity | 5.3.C.
Output | 5.4 | 0 | 0 | 0
Activity | 5.4.A.
Activity | 5.4.B.
Activity | 5.4.C.
Output | 5.5 | 0 | 0 | 0
Activity | 5.5.A.
Activity | 5.5.B.
Activity | 5.5.C.

## j. Workplan
The Work Plan is a supplemental document often required for proposal development. The Work Plan outlines when each proposed project objective will take place over the life of the project. For some objective statements, such as the goal, may occur throughout the project. Some, such as a training program by extension workers, may only occur in one month of a five-year project. Included in the Work Plan is a guideline for tracking who is responsible for the completion of specific objectives. In some cases, this may be an individual, but in larger consortiums, this may be a place to indicate that a proposed partner is responsible for completion of a specific objective.
Project Title
|  | Objective Statement | Year 1 | [11 empty] | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Where | Person/Organization Responsible | Budget Required | Budget Narrative
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
GOAL: |  | 0
Outcome | 1 | 0
Output | 1.1 | 0
Activity | 1.1.A.
Activity | 1.1.B.
Activity | 1.1.C.
Activity | 1.1.D.
Activity | 1.1.E.
Output | 1.2 | 0
Activity | 1.2.A.
Activity | 1.2.B.
Activity | 1.2.C.
Activity | 1.2.D.
Activity | 1.2.E.
Output | 1.3 | 0
Activity | 1.3.A.
Activity | 1.3.B.
Activity | 1.3.C.
Activity | 1.3.D.
Activity | 1.3.E.
Output | 1.4 | 0
Activity | 1.4.A.
Activity | 1.4.B.
Activity | 1.4.C.
Activity | 1.4.D.
Activity | 1.4.E.
Output | 1.5 | 0
Activity | 1.5.A.
Activity | 1.5.B.
Activity | 1.5.C.
Activity | 1.5.D.
Activity | 1.5.E.
Outcome | 2 | 0
Output | 2.1 | 0
Activity | 2.1.A.
Activity | 2.1.B.
Activity | 2.1.C.
Activity | 2.1.D.
Activity | 2.1.E.
Output | 2.2 | 0
Activity | 2.2.A.
Activity | 2.2.B.
Activity | 2.2.C.
Activity | 2.2.D.
Activity | 2.2.E.
Output | 2.3 | 0
Activity | 2.3.A.
Activity | 2.3.B.
Activity | 2.3.C.
Activity | 2.3.D.
Activity | 2.3.E.
Output | 2.4 | 0
Activity | 2.4.A.
Activity | 2.4.B.
Activity | 2.4.C.
Activity | 2.4.D.
Activity | 2.4.E.
Output | 2.5 | 0
Activity | 2.5.A.
Activity | 2.5.B.
Activity | 2.5.C.
Activity | 2.5.D.
Activity | 2.5.E.
Outcome | 3 | 0
Output | 3.1 | 0
Activity | 3.1.A.
Activity | 3.1.B.
Activity | 3.1.C.
Activity | 3.1.D.
Activity | 3.1.E.
Output | 3.2 | 0
Activity | 3.2.A.
Activity | 3.2.B.
Activity | 3.2.C.
Activity | 3.2.D.
Activity | 3.2.E.
Output | 3.3 | 0
Activity | 3.3.A.
Activity | 3.3.B.
Activity | 3.3.C.
Activity | 3.3.D.
Activity | 3.3.E.
Output | 3.4 | 0
Activity | 3.4.A.
Activity | 3.4.B.
Activity | 3.4.C.
Activity | 3.4.D.
Activity | 3.4.E.
Output | 3.5 | 0
Activity | 3.5.A.
Activity | 3.5.B.
Activity | 3.5.C.
Activity | 3.5.D.
Activity | 3.5.E.
Outcome | 4 | 0
Output | 4.1 | 0
Activity | 4.1.A.
Activity | 4.1.B.
Activity | 4.1.C.
Activity | 4.1.D.
Activity | 4.1.E.
Output | 4.2 | 0
Activity | 4.2.A.
Activity | 4.2.B.
Activity | 4.2.C.
Activity | 4.2.D.
Activity | 4.2.E.
Output | 4.3 | 0
Activity | 4.3.A.
Activity | 4.3.B.
Activity | 4.3.C.
Activity | 4.3.D.
Activity | 4.3.E.
Output | 4.4 | 0
Activity | 4.4.A.
Activity | 4.4.B.
Activity | 4.4.C.
Activity | 4.4.D.
Activity | 4.4.E.
Output | 4.5 | 0
Activity | 4.5.A.
Activity | 4.5.B.
Activity | 4.5.C.
Activity | 4.5.D
Activity | 4.5.E.
Outcome | 5 | 0
Output | 5.1 | 0
Activity | 5.1.A.
Activity | 5.1.B.
Activity | 5.1.C.
Activity | 5.1.D.
Activity | 5.1.E.
Output | 5.2 | 0
Activity | 5.2.A.
Activity | 5.2.B.
Activity | 5.2.C.
Activity | 5.2.D.
Activity | 5.2.E.
Output | 5.3 | 0
Activity | 5.3.A.
Activity | 5.3.B.
Activity | 5.3.C.
Activity | 5.3.D
Activity | 5.3.E.
Output | 5.4 | 0
Activity | 5.4.A.
Activity | 5.4.B.
Activity | 5.4.C.
Activity | 5.4.D.
Activity | 5.4.E.
Output | 5.5 | 0
Activity | 5.5.A.
Activity | 5.5.B.
Activity | 5.5.C.
Activity | 5.5.D.
Activity | 5.5.E.