## a. Design Workbook Instructions
TOOL SUMMARY: PROJECT DESIGN WORKBOOK INSTRUCTIONS
Purpose | The purpose of the Project Design Workbook is to consolidate and link in ONE document the final drafts of all the project design tools. Each tab represents a different design tool. The tabs include:
· Problem Analysis
· Problem to Objective
· Results Framework
· Logframe
· Work Plan
* Two versions of the Workbook are provided: This one with the instructions is intended to help you work through each step and the one without instructions is intended for you to use to submit the final drafts of each tool.
Information Sources | There are no information sources for the Project Design Workbook, it consolidates the tools outlined above.
Who | The project design should be coordinated/facilitated by one person who leads the entire design process. The factors to consider when determining the lead for this process are:
· Familiarity with target population
· Familiarity with the results from the needs assessment
· Experience using the tools described in the Purpose.
* For further guidance on creating proposals for restricted grants and who leads the design process in these cases please refer to the LWR Grants Acquisition Manual p. 41.
When | The final draft of each project design tool should be included in the Project Design Workbook upon its completion. The entire Project Design Workbook should be completed and submitted as part of unrestricted LWR project proposals.
Requirements | REQUIREMENTS:
· All UNRESTRICTED projects are required to complete the Project Design Workbook so that the entire design is captured. The completion of this document forms the foundation of the technical and cost proposals, as it outlines the entire project design.
RECOMMENDATIONS:
· Completion of the Project Design Workbook is recommended for all RESTRICTED project proposals, understanding that the templates may need to be adjusted to meet donor requirements.
· The Work Plan is a supplemental document often required for proposal development. It is important to document this as it helps in monitoring and tracking spending, schedules and budgets. Included in the Work Plan is a guideline for tracking who is responsible for the completion of specific activities. In some cases, this may be an individual, but in larger consortiums, this may be a place to indicate that a proposed partner is responsible for completion of a specific result.
Tips | The final three templates (results framework, logframe, work plan) of the Project Design Workbook are designed to be used together and are linked with the Problems to Objectives to help reduce the need to input information multiple times. If this function is not useful, do what is most practical.
If you would rather work in a format other than Excel: Working in formats other than Excel (Word, PowerPoint, etc.) is often easier than working in Excel, in particular for tools that require lots of narrative. Therefore, these other formats can be used for the working drafts of each tool in the Project Design Workbook. Once the final draft has been completed it can simply be copied and transferred to the Excel template.
· If a different format is used, the easiest way to copy it into the Excel file is to use the “Snipping Tool” which is a Microsoft tool found in the Start Menu: All Programs – Accessories – Snipping Tool. Select and copy the whole graphic and paste it into the Project Design Workbook. The Snipping tool can be used to copy and paste from any electronic medium, including websites, Microsoft Office applications, etc.
Gender Considerations | Where necessary, the Project Design Workbook provides guidance on how to integrate gender into each of the tabs in this workbook. The Gender Considerations section provides standards for gender integration. Additional information and resources can be found in the Learning for Gender Integration Manual and among the DMEL Additional Resources provided on dmel.lwr.org.

## b. Problem Analysis Summary
TOOL SUMMARY: PROBLEM ANALYSIS
Purpose | The purpose of a Problem Analysis is to study of one or more problems (identified during the Needs Assessment stage) by identifying the problem’s underlying causes and the effects (negative) that it creates.
· LWR recommends using the Problem Tree method to facilitate this analysis.
Information Sources | Information the project design team should have before starting the Problem Analysis:
· Needs Assessment data
· Project team experience
Guidance for Problem Analysis:
· IFRC Project Planning Guidance Manual: 4.1.4: Problem analysis using the “problem tree” tool (P. 21-22)
· IFRC Project Planning Guidance Manual: Annex 1: How to create a problem tree (P. 51-53)
· CRS Problem Tree guidance (P. 76-82)
· Problem Tree template
Who | The Problem Analysis should be coordinated/facilitated by the same person who leads the entire design process. The factors to consider when determining the lead for this process are:
* For further guidance on creating proposals for restricted grants and who leads the design process in these cases please refer to the LWR Grants Acquisition Manual p. 41.
· Familiarity with the results from the Needs Assessment
· Experience using the Problem Tree method.
Doing the Problem Analysis with participation of representatives of the target population is ideal. The target population is most familiar with the problems and the context.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual p. 41.
When | The Problem Analysis comes after the Needs Assessment data has been collected and before moving to the Results Framework.
Requirements | REQUIREMENTS:
· The Problem Analysis is required for all UNRESTRICTED projects, and the Problem Tree is the recommended method for this analysis.
· Each problem, cause, and effect should have some sort of evidence that verifies it is true. The evidence and source should be noted while doing the problem analysis and documented in the Problems to Objectives tool once the analysis is completed.
· For some RESTRICTED proposals the donor may specify the problem statement or the causes, or both. Use any templates provided by the donor for this analysis.
· In cases where the problem statement is provided, then the Problem Analysis should focus on determining only the causes of that problem. The analysis of the causes should still be based on what is known about the target area/population as a result of the Needs Assessment.
o If both the problem statement and the causes are specified by the donor, the Problem Analysis is NOT required. The design team can move directly to the Results Framework.
RECOMMENDATIONS:
· The process is as important as the product. The exercise should be treated as a learning experience and an opportunity for different views and interests to be expressed.
· If necessary, the unclear aspects of a problem can be further elaborated through additional focus groups and/or interviews with the target population.
· The most common method for doing a participatory Problem Tree analysis is with sticky notes or note cards where one problem, cause or effect is placed on each card. This allows the participants to move the cards around and discuss where they best fit within the Problem Analysis.
Tips | While the project will not be able to address every problem identified in the Needs Assessment, this analysis should incorporate all problems identified to create the full context in which the project will exist.
· Sometimes the project team will simply know that a problem or cause exists from many years of interaction with the target population or zone.
o Nevertheless, it is a good exercise to reaffirm what is known by conducting a new needs assessment or undertaking a short investigation of relevant studies or government data for the area when proposing a new project.
· Completing the problem analysis can be complex, therefore experience in facilitating the use of the Problem Tree method and familiarity with the local context is of utmost importance when selecting a lead coordinator/facilitator.
· Does each cause-effect link (illustrated by arrows) make sense? Is each link plausible? Why or why not?
· How well have the causes gone down to the roots? Are there any unidentified root causes?
· What appears to be the relative contribution of each causal stream (causes linked by arrows leading to the core problem statement) to the problem? Do some causes appear more than once? Why is this? Which causes show significant influence?
· Depending on the depth of analysis, the lowest cause identified in the Problem Analysis can relate directly to chosen activities.
Any method or program can be used to document the results of the Problem Analysis in the Project Design Workbook. What is important is that the results are documented.
· The example provided is a typical graphical presentation of a Problem Tree. The use of this word template is not required. The graphic can be manipulated (size and number of boxes) to reflect the results of the Problem Tree analysis.
o If the Word template is used, it must be transferred to the Project Design Workbook once completed. To do so, the easiest way is to use the “Snipping Tool” which is a Microsoft tool found in the Start Menu: All Programs – Accessories – Snipping Tool. Select and copy the whole graphic and paste it into the Project Design Workbook in the Problem Analysis Documentation tab. The Snipping tool can be used to copy and paste from any electronic medium, including websites, Microsoft Office applications, etc.
o An alternative option is to take a photo of the results and paste it into the Project Design Workbook.
· Some online applications can make collaborating in the development of the Problem Tree much easier. Two options include Padlet (www.padlet.com) or C-MAPS (http://cmap.ihmc.us/download/). For more information contact your regional M&E manager.
Gender Considerations | A project that meets the LGI standards for gender integration at this stage will undertake all of the following:
· Identifies key gender-based constraints in the targeted area or related to the sector including:
o Conditions of disparity
o Factors causing the identified inequalities
· Includes gender-based constraints in gender-specific problem tree and/or general Problem Analysis tab in the Project Design Workbook.
· Prioritizes and link GBCs to other problems identified.
o There may be GBCs that are NOT directly linked to other problems but which may still be important to address. These can become individual objectives.

## c. Problem Analysis Doc.
Instructions: The easiest way to insert a final draft of the Problem Tree analysis into the Project Design Workbook is to use the “Snipping Tool” which is a Microsoft tool found in the Start Menu: All Programs – Accessories – Snipping Tool. Select and copy the whole graphic and paste it into the Project Design Workbook in the Problem Analysis Documentation tab. The Snipping Tool can be used to copy and paste from any electronic medium, including websites, Microsoft Office applications, etc.
KEY: Any method or program can be used to document the results of the Problem Analysis in the Project Design Workbook, including a photo of the document the group uses to work through this analysis. What is important is that the results are documented and can be clearly read.
Below is an example of a Word template pasted in the tab using the Snipping Tool. Simply delete this example and paste your finalized Problem Analysis results when it is completed.
* For further guidance on creating proposals for restricted grants and who leads the design process in these cases please refer to the LWR Grants Acquisition Manual p. 41.

## d. Problem to Objective Summary
TOOL SUMMARY: PROBLEMS TO OBJECTIVES
Purpose | The purpose of the Problems to Objectives tool is two-fold:
1. It documents the links between the problems/causes and their evidence. It does this by linking information from the Problem Analysis and a citation to the document that provides the evidence that confirms the existence and degree of each problem and cause.
o For example: "reduced agricultural output in the priority action zone" is the problem, and the evidence with citation could be “Agricultural output in the PAZ has decreased by 25% from 2011-2013 (Needs Assessment section 2.1).”
2. It documents the links between the current negative condition and the desired future positive condition. The current negative condition is documented in the problems and causes from the Problem Analysis. The expected results of the project (solution) are the inverse of the problem/cause and are written as objective statements (as described in the Logframe Cheat Sheet).
o For example: "reduced agricultural output in the priority action zone" is the problem, and the expected result is “The target beneficiaries in the PAZ have increased agricultural output.”
Information Sources | Information the project design team should have before starting the Problems to Objectives:
· Needs Assessment data
· Problem Analysis results
Who | The completion of the Problems to Objectives tab should be coordinated/facilitated by the same person who leads the entire project design process.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual p. 41.
When | The Problems to Objectives should be completed after the Problem Analysis has been finalized. The final Problem Analysis is transferred to the first column of the spreadsheet and the evidence and source is noted in the second column. This should be done before moving on to the Results Framework.
Requirements | REQUIREMENTS:
· The Problems to Objectives tab is required for all UNRESTRICTED projects.
· All columns in the Problems to Objectives tab must be filled in:
o The Problem/Cause column is filled in with the final results from the Problem Analysis
o The Evidence of Problem/Cause with Citation column should be completed while the problems and causes are being identified, and confirmed and entered into this column after they have been finalized.
o The Objective Statement column can be filled in using the Objectives Development Guide. This is transferred directly to the Results Framework where the IF-THEN logic can be tested.
RECOMMENDATIONS:
· The Problems to Objectives tab is recommended for all proposals for RESTRICTED funding.
Tips | · It is recommended that the problem statement and each cause identified be linked to data that verifies its existence in the target population and the degree to which it affects the target population.
o For example: if the project goal is "improved agricultural productivity," the corresponding description of the cause would be "poor agricultural productivity in the target area." The degree to which the cause affects the target population would be represented by specific data that would verify “how poor” the agricultural productivity is in the area (i.e. 50% reduction from average in the past year).
o The documented source may be a LWR needs assessment, peer agency needs assessment, government report, agency report, or other published document
o This source is documented in the Project Design Workbook in the Problems to Objectives tab.
· If you know a problem or cause will NOT be included in the end project design, you do not have to complete this column for that Problem or Cause.
· Sometimes the project team will simply know that a problem or cause exists from many years of interaction with the target population or zone.
o Nevertheless, it is a good exercise to reaffirm what is known by conducting a new Needs Assessment or undertaking a short investigation of relevant studies or government data for the area when proposing a new project.”
· Double check that each objective statement is written according to the guidelines outlined in the Logframe Cheat Sheet.
· Double check that each objective statement is the inverse of the problem or cause to which it is linked.
Gender Considerations | A project that meets the LGI standards for gender integration at this stage will undertake all of the following:
· References information gathered during the Needs Assessment as evidence in the Problems to Objectives tab in the Design Workbook.
· If necessary, identifies specific objectives that will address the gender-based constraints identified.

## e. Problems to Objectives
Explanation | The PROBLEM/CAUSE column: Enter the problems and causes from the Problem Analysis. Remember, the problems and causes are the actual situation in the target area expressed as the negative condition. | The EVIDENCE FOR PROBLEM/CAUSE W/CITATION column is a way to document the source of the evidence for each problem or cause. It helps ensure that the problems and causes identified in the project design are based on actual or observed situations. It is a way to document what is found in the Needs Assessment, but can also come from peer agency needs assessments, government reports, agency reports, or another published document. The document or source of the evidence for each problem/cause should be written in parenthesis after the evidence. For example, if the Problem is "poor agricultural productivity in the priority action zone," then the evidence with citation could be “Agricultural output in the PAZ has decreased by 25% from 2011-2013 (Needs assessment section 2.1).” The citation helps document key information and can also assist in setting indicators or beneficiary targets. |  | The OBJECTIVE STATEMENT column is where the project's objectives are documented. Having this column on the same page as the PROBLEM/CAUSE helps ensure that the proposed objective responds to the problems/causes identified during the assessment stage. The objectives statements are the opposite of negative condition identified in the Problem Analysis. They are written as the positive condition and as if the result has already been achieved. The Objective Analysis Tool Summary, as well as the guidance in the sections related to the objective analysis in the IFRC Project Planning Guidance, can assist in selecting the most appropriate objectives for the context of the project. The Results Framework can then be used to verify the logic between the selected Goal, Outcomes, and Outputs.
Project Title:
# | PROBLEM/CAUSE | EVIDENCE FOR PROBLEM-CAUSE W/ CITATION | # | OBJECTIVE STATEMENT
Problem 1 |  |  | GOAL:
Cause 1 |  |  | Outcome 1
Cause 1.2 |  |  | Output 1.1
Cause 1.3 |  |  | Output 1.2
Cause 1.4 |  |  | Output 1.3
Cause 1.5 |  |  | Output 1.4
Cause 1.6 |  |  | Output 1.5
Cause 2 |  |  | Outcome 2
Cause 2.1 |  |  | Output 2.1
Cause 2.2 |  |  | Output 2.2
Cause 2.3 |  |  | Output 2.3
Cause 2.4 |  |  | Output 2.4
Cause 2.5 |  |  | Output 2.5
Cause 3 |  |  | Outcome 3
Cause 3.1 |  |  | Output 3.1
Cause 3.2 |  |  | Output 3.2
Cause 3.3 |  |  | Output 3.3
Cause 3.4 |  |  | Output 3.4
Cause 3.5 |  |  | Output 3.5
Cause 4 |  |  | Outcome 4
Cause 4.1 |  |  | Output 4.1
Cause 4.2 |  |  | Output 4.2
Cause 4.3 |  |  | Output 4.3
Cause 4.4 |  |  | Output 4.4
Cause 4.5 |  |  | Output 4.5
Cause 5 |  |  | Outcome 5
Cause 5.1 |  |  | Output 5.1
Cause 5.2 |  |  | Output 5.2
Cause 5.3 |  |  | Output 5.3
Cause 5.4 |  |  | Output 5.4
Cause 5.5 |  |  | Output 5.5

## f. Results Framework Summary
TOOL SUMMARY: RESULTS FRAMEWORK
Purpose | The purpose of the Results Framework is to visually document all the project’s objectives (Outputs, Outcomes, Goal), which helps when verifying the “if-then” logic between the project’s results.
· A Results Framework is the solution to the problem outlined in the Problem Analysis.
Information Sources | Information the project design team should have before starting the Results Framework:
· Needs Assessment data
· Problem Analysis results
· Problems to Objectives
Guidance for completing the Results Framework:
· USAID Tips: BUILDING A RESULTS FRAMEWORK
· Logframe Cheat Sheet
o For properly writing objective statements
Who | The completion of the Results Framework should be coordinated/facilitated by the same person who leads the entire project design process.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual p. 41.
When | The Results Framework is completed after completing the Problems to Objectives and provides the content for the project results column of the Logframe.
Requirements | REQUIREMENTS:
· The Results Framework is required for all projects.
RECOMMENDATIONS:
· LWR recommends using only 4 levels of results (Goal, Outcome, Output, Activities), but recognizes that some projects may require an Intermediate Result, in particular projects with large scopes.
o Intermediate Results would fall between the Outputs and Outcomes and would follow the same formula for writing the objective statement as the Outputs and Outcomes. Outputs (or multiple Outputs) would lead to an Intermediate Result and Intermediate Results (or multiple Intermediate Results) would lead to the Outcome.
o Intermediate Results are normally identified as necessary during the development of the Results Framework and reflect Problem Analysis results that have more than 3 levels of causes. There must be a continued strong “if-then” logic between the Intermediate Results and the Outcomes and Outputs linked to it.
· The project design team can use the Word format provided to create the Results Framework.
o The graphic can be manipulated (size and number of boxes) to reflect the number of objective statements (Goals, Outcomes, Outputs) for the project.
o If the Word template is used it must be transferred to the Project Design Workbook under the Results Framework tab once completed.
Tips | · Identify different ways to involve stakeholders in project review and adaptation. Build in flexibility to respond to unplanned opportunities.
· The Results Framework also conveys the development hypothesis, or theory of change, implicit in the strategy and the cause-and-effect linkages between the intermediate results and the goal.
· The Results Framework is normally developed from the Goal down to the Activities, but it may be easier to skip around among different levels to some extent. That is fine, because in fact, it is the way creating a results framework sometimes proceeds!
· Ensure the logic between each level of your objectives by using the “if – and- then” test.
o For example: IF…the partner conducts disaster management trainings (activity)…AND…the communities don’t have any unplanned demands on their time (assumption)…THEN…communities have improved awareness of measures to prepare for and respond to disasters (output).
Gender Considerations | A project that meets the LGI standards for gender integration at this stage will undertake all of the following:
· Clear IF-THEN logic between outputs and activities, and gender-based constraints (outcomes).

## g. Results Framework
The following 3 templates (Results Framework, Logframe, Work Plan) are designed to be used together and some cells are linked. When you enter information into the Results Framework, it automatically fills in details in the Logical Framework and Work Plan. This ensures that the objectives statements are consistent throughout the document. If edits are made to the objective statements, only make changes in the Results Framework. Because the Results Framework, LogFrame, and WorkPlan are linked, it is very important to NOT modify the formulas in the objective statement columns of the Evidence for Cause, Logframe and Work Plan tabs. If you have any questions about modifying these templates, please contact the M&E Unit for technical support.
Project Title | 0
GOAL: | 0
Outcome |  | Outcome |  | Outcome |  | Outcome |  | Outcome
1 |  | 2 |  | 3 |  | 4 |  | 5
0 |  | 0 |  | 0 |  | 0 |  | 0
| Output |  | Output |  | Output |  | Output |  | Output
| 1.1 |  | 2.1 |  | 3.1 |  | 4.1 |  | 5.1
| 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1.2 |  | 2.2 |  | 3.2 |  | 4.2 |  | 5.2
| 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1.3 |  | 2.3 |  | 3.3 |  | 4.3 |  | 5.3
| 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1.4 |  | 2.4 |  | 3.4 |  | 4.4 |  | 5.4
| 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1.5 |  | 2.5 |  | 3.5 |  | 4.5 |  | 5.5
| 0 |  | 0 |  | 0 |  | 0 |  | 0

## h. Logframe Summary
TOOL SUMMARY: LOGFRAME
Purpose | The purpose of the Logframe is to SUMMARIZE the entirety of the project’s logic by outlining its expected results (Goal, Outcome, Output, Activities), how the achievement of the results will be measured (indicators), how the data to measure the results will be collected and verified (Means of Verification), and the assumptions made about the logic between each level of the expected results (Assumptions).
· The Logframe matrix consists of a table with four main columns, in which design and data collection aspects of a project are summarized. It sets out a logical sequence of cause-effect relationships based on the results chain/objectives hierarchy.
· It is a living document, which should be consulted and altered throughout the project’s life cycle.
Information Sources | Information the project design team should have before starting the Logframe:
· Needs Assessment data
· Problem Analysis
· Problems to Objectives
· Results Framework
Guidance for Logframe development:
· Project indicators or standard indicator lists
· Logframe Cheat Sheet
· Logframe Guidance
· Logframe Master Translator
Who | The development of the project’s Logframe is one of the most important components of the project’s design. Many people will be involved in developing the Logframe, but one person should be assigned responsibility during the proposal kickoff meeting to manage feedback, do version control, and ensure that the final draft is completed on time.
· It is good to have one reviewer of the Logframe who is not part of the core proposal development team. An outside perspective can help identify gaps in logic or missing details resulting from the familiarity of the proposal development team with the project proposal.
* For further guidance on the grants acquisition process please refer to the LWR Grants Acquisition Manual p. 41.
When | The Logframe is developed after the Results Framework is completed and before the Work Plan is finalized
Requirements | REQUIREMENTS:
· The Logframe is required for all UNRESTRICTED projects.
· This Logframe template is the most widely accepted template by major donors, with the main variations being the different terminology for objectives (Output, Outcome, Goal).
· For projects using LWR UNRESTRICTED funding, the terminology used in the LWR Logframe should be followed.
· The IFRC Project Planning Guidance Manual has an example of a Logframe on page 40, but uses slightly different terminology than what is proposed in this example and LWR’s Logframe Cheat Sheet. IFRC’s example can be used as an additional reference, but LWR’s terminology should be used as the standard.
· For projects with RESTRICTED funding, the terminology used by the donor should be used when creating the Logframe. Please refer to the Logframe Master Translator to understand more clearly how donor terms match with LWR standard terms.
RECOMMENDATIONS:
· The blank Word logframe template can be used when brainstorming and editing the content of the logframe. Once a draft of the logframe is completed the content should be transferred to the Project Design Workbook by copying the content into the corresponding cells in the Logframe tab.
· Activities, not tasks, should be included in the Logframe. Their inclusion ensures the activities will lead to their corresponding Output. Activities will not have indicators in the Logframe. The target number of activities and the timeframe for completing them is included in the project’s Work Plan.
· In the example in Logframe Guidance, you will see that for Outcome 1, targets for the INDICATORS are placed in parentheses after the indicator. This method can be used if indicator targets are known at this stage (primarily from reliable data obtained during the Needs Assessment), but often indicator targets are not finalized until baseline data has been collected. Finalized indicator targets should be documented in the project's Indicator Tracking Table which is developed during the DMEL Process: Develop detailed M&E plan.
SMART Criteria:
· SMART criteria are: Specific, Measurable, Attainable, Relevant, and Timebound.
· It is recommended that objective statements in the Logframe are NOT written using SMART criteria.
o Nevertheless, SMART objective statements can sometimes be used effectively within project proposals to show all the details of the expected result in one statement.
· SMART criteria should be applied to indicators, not objective statements. (reference p. 37 of IFRC Project Planning Guidance Manual for further information on SMART criteria).
· Follow the instructions and examples for writing indicators found in the Logframe Cheat Sheet.
· As presented in the Logframe, each indicator may not meet all the SMART criteria, but once the M&E Plan Matrix is fully developed the indicators should be SMART.
Tips | The objectives outlined in the Results Framework are transferred to the first column of the Logframe and then work begins on completing the remaining three columns (indicators, means of verification, assumptions). The completed Logframe will be the foundation for completing the M&E Plan Matrix in the DMEL Process of Create detailed M&E plan.
· Identify different ways to involve stakeholders in project review and adaptation. Build in flexibility to respond to unplanned opportunities.
· You might not work down from Goal to Activities in a perfectly linear fashion. It may be easier to skip around among different levels to some extent. That is fine, because in fact, it is the way creating a logframe sometimes proceeds!
· Ensure the logic between each level of your objectives by using the “if – and- then” test.
o For example: IF…the partner conducts disaster management trainings (activity)…AND…the communities don’t have any unplanned demands on their time (assumption)…THEN…communities have improved awareness of measures to prepare for and respond to disasters (output).
· Do not over-specify activities. This can cause you to spend less time on the more important elements of the logframe (Outcome and Output level objectives).
· It is always helpful to define the duration of your proposed project. This will certainly help you to be realistic in finalizing your outcomes, i.e. what is achievable by the end of project.
· It is important to monitor critical assumptions during implementation. Your M&E Plan should include this responsibility.
· You do not need to have an assumption at each level in the final draft of your logframe; this is not an exercise to fill in all of the boxes!
· Always be realistic in setting targets. Support your arguments for the ones you do set (ideally from benchmark data), and also for the ones you can’t!
· How many indicators? Stick to the “less is more” principle.
· All additional project documents should refer to and be developed based upon the Logframe.
· The Logframe does not show every detail of a project. Further details, such as the proposal, budget, Detailed M&E Plan, and activity schedule, can be provided in other documents that accompany the Logframe.
Gender Considerations | A project that meets the LGI standards for gender integration at this stage will undertake all of the following:
· Clearly identify that individual (people)-level indicators will be sex-disaggregated.
· Aim to disaggregate other indicators by sex, age, and other variables. For example, production indicators will be disaggregated by the sex of the plot manager, adoption of technology will be disaggregated by sex of the farmer who adopts .
* If there are any GBCs (or causes) that did not become objectives and are not included in the results framework, consider whether these should be included in the logframe as assumptions or risks

## i. LogFrame
Project Title |  |  |  | 0
|  | PROBLEM/CAUSE | EVIDENCE OF PROBLEM-CAUSE WITH CITATION | OBJECTIVE STATEMENT | OBJECTIVELY VERIFIABLE INDICATOR | MEANS OF VERIFICATION | RISK AND ASSUMPTION
GOAL: |  | 0 | 0 | 0
Outcome | 1 | 0 | 0 | 0
Output | 1.1 | 0 | 0 | 0
Activity | 1.1.A.
Activity | 1.1.B.
Activity | 1.1.C.
Output | 1.2 | 0 | 0 | 0
Activity | 1.2.A.
Activity | 1.2.B.
Activity | 1.2.C.
Output | 1.3 | 0 | 0 | 0
Activity | 1.3.A.
Activity | 1.3.B.
Activity | 1.3.C.
Output | 1.4 | 0 | 0 | 0
Activity | 1.4.A.
Activity | 1.4.B.
Activity | 1.4.C.
Output | 1.5 | 0 | 0 | 0
Activity | 1.5.A.
Activity | 1.5.B.
Activity | 1.5.C.
Outcome | 2 | 0 | 0 | 0
Output | 2.1 | 0 | 0 | 0
Activity | 2.1.A.
Activity | 2.1.B.
Activity | 2.1.C.
Output | 2.2 | 0 | 0 | 0
Activity | 2.2.A.
Activity | 2.2.B.
Activity | 2.2.C.
Output | 2.3 | 0 | 0 | 0
Activity | 2.3.A.
Activity | 2.3.B.
Activity | 2.3.C.
Output | 2.4 | 0 | 0 | 0
Activity | 2.4.A.
Activity | 2.4.B.
Activity | 2.4.C.
Output | 2.5 | 0 | 0 | 0
Activity | 2.5.A.
Activity | 2.5.B.
Activity | 2.5.C.
Outcome | 3 | 0 | 0 | 0
Output | 3.1 | 0 | 0 | 0
Activity | 3.1.A.
Activity | 3.1.B.
Activity | 3.1.C.
Output | 3.2 | 0 | 0 | 0
Activity | 3.2.A.
Activity | 3.2.B.
Activity | 3.2.C.
Output | 3.3 | 0 | 0 | 0
Activity | 3.3.A.
Activity | 3.3.B.
Activity | 3.3.C.
Output | 3.4 | 0 | 0 | 0
Activity | 3.4.A.
Activity | 3.4.B.
Activity | 3.4.C.
Output | 3.5 | 0 | 0 | 0
Activity | 3.5.A.
Activity | 3.5.B.
Activity | 3.5.C.
Outcome | 4 | 0 | 0 | 0
Output | 4.1 | 0 | 0 | 0
Activity | 4.1.A.
Activity | 4.1.B.
Activity | 4.1.C.
Output | 4.2 | 0 | 0 | 0
Activity | 4.2.A.
Activity | 4.2.B.
Activity | 4.2.C.
Output | 4.3 | 0 | 0 | 0
Activity | 4.3.A.
Activity | 4.3.B.
Activity | 4.3.C.
Output | 4.4 | 0 | 0 | 0
Activity | 4.4.A.
Activity | 4.4.B.
Activity | 4.4.C.
Output | 4.5 | 0 | 0 | 0
Activity | 4.5.A.
Activity | 4.5.B.
Activity | 4.5.C.
Outcome | 5 | 0 | 0 | 0
Output | 5.1 | 0 | 0 | 0
Activity | 5.1.A.
Activity | 5.1.B.
Activity | 5.1.C.
Output | 5.2 | 0 | 0 | 0
Activity | 5.2.A.
Activity | 5.2.B.
Activity | 5.2.C.
Output | 5.3 | 0 | 0 | 0
Activity | 5.3.A.
Activity | 5.3.B.
Activity | 5.3.C.
Output | 5.4 | 0 | 0 | 0
Activity | 5.4.A.
Activity | 5.4.B.
Activity | 5.4.C.
Output | 5.5 | 0 | 0 | 0
Activity | 5.5.A.
Activity | 5.5.B.
Activity | 5.5.C.

## j. Workplan
The Work Plan is a supplemental document often required for proposal development. The Work Plan outlines when each proposed project objective will take place. Some objective statements, such as the goal, may occur throughout the project. Others, such as a training program by extension workers, may only occur in one month of a five-year project. Included in the Work Plan is a guideline for tracking who is responsible for specific objectives. In some cases, this may be an individual; in larger consortia, this may refer to the partner responsible for the objective.
Project Title |  | 0
|  | Objective Statement | Year 1 | [11 empty] | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Where | Person/Organization Responsible | Budget Required | Budget Narrative
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
GOAL: |  | 0
Outcome | 1 | 0
Output | 1.1 | 0
Activity | 1.1.A. | 0
Activity | 1.1.B. | 0
Activity | 1.1.C. | 0
Output | 1.2 | 0
Activity | 1.2.A. | 0
Activity | 1.2.B. | 0
Activity | 1.2.C. | 0
Output | 1.3 | 0
Activity | 1.3.A. | 0
Activity | 1.3.B. | 0
Activity | 1.3.C. | 0
Output | 1.4 | 0
Activity | 1.4.A. | 0
Activity | 1.4.B. | 0
Activity | 1.4.C. | 0
Output | 1.5 | 0
Activity | 1.5.A. | 0
Activity | 1.5.B. | 0
Activity | 1.5.C. | 0
Outcome | 2 | 0
Output | 2.1 | 0
Activity | 2.1.A. | 0
Activity | 2.1.B. | 0
Activity | 2.1.C. | 0
Output | 2.2 | 0
Activity | 2.2.A. | 0
Activity | 2.2.B. | 0
Activity | 2.2.C. | 0
Output | 2.3 | 0
Activity | 2.3.A. | 0
Activity | 2.3.B. | 0
Activity | 2.3.C. | 0
Output | 2.4 | 0
Activity | 2.4.A. | 0
Activity | 2.4.B. | 0
Activity | 2.4.C. | 0
Output | 2.5 | 0
Activity | 2.5.A. | 0
Activity | 2.5.B. | 0
Activity | 2.5.C. | 0
Outcome | 3 | 0
Output | 3.1 | 0
Activity | 3.1.A. | 0
Activity | 3.1.B. | 0
Activity | 3.1.C. | 0
Output | 3.2 | 0
Activity | 3.2.A. | 0
Activity | 3.2.B. | 0
Activity | 3.2.C. | 0
Output | 3.3 | 0
Activity | 3.3.A. | 0
Activity | 3.3.B. | 0
Activity | 3.3.C. | 0
Output | 3.4 | 0
Activity | 3.4.A. | 0
Activity | 3.4.B. | 0
Activity | 3.4.C. | 0
Output | 3.5 | 0
Activity | 3.5.A. | 0
Activity | 3.5.B. | 0
Activity | 3.5.C. | 0
Outcome | 4 | 0
Output | 4.1 | 0
Activity | 4.1.A. | 0
Activity | 4.1.B. | 0
Activity | 4.1.C. | 0
Output | 4.2 | 0
Activity | 4.2.A. | 0
Activity | 4.2.B. | 0
Activity | 4.2.C. | 0
Output | 4.3 | 0
Activity | 4.3.A. | 0
Activity | 4.3.B. | 0
Activity | 4.3.C. | 0
Output | 4.4 | 0
Activity | 4.4.A. | 0
Activity | 4.4.B. | 0
Activity | 4.4.C. | 0
Output | 4.5 | 0
Activity | 4.5.A. | 0
Activity | 4.5.B. | 0
Activity | 4.5.C. | 0
Outcome | 5 | 0
Output | 5.1 | 0
Activity | 5.1.A. | 0
Activity | 5.1.B. | 0
Activity | 5.1.C. | 0
Output | 5.2 | 0
Activity | 5.2.A. | 0
Activity | 5.2.B. | 0
Activity | 5.2.C. | 0
Output | 5.3 | 0
Activity | 5.3.A. | 0
Activity | 5.3.B. | 0
Activity | 5.3.C. | 0
Output | 5.4 | 0
Activity | 5.4.A. | 0
Activity | 5.4.B. | 0
Activity | 5.4.C. | 0
Output | 5.5 | 0
Activity | 5.5.A. | 0
Activity | 5.5.B. | 0
Activity | 5.5.C. | 0