## a. Detail M&E Plan Instructions
LWR Detailed M&E Plan Instructions
1. Complete the M&E Matrix: It can be developed within the tab or within a Word document and transferred to the M&E Matrix tab.
a. For detailed instructions on completing the content of the M&E Matrix, please refer to tab c. M&E Matrix Cheat Sheet.
b. Enter the objective statements and indicators ONLY in the M&E Matrix. They are automatically linked to the Indicator Tracking Table (ITT) and the Activity Tracking Table (ATT).
2. Baseline Table:
a. Fill in the Baseline Table after or as the baseline data is collected either by a consultant or the project team.
3. Complete the Indicator Tracking Table: See tab i. for further instructions on using the ITT.
a. Fill in the Project Name and the Project Year (PY) for the ITT. The blank version of this workbook contains linked ITT and ATT tables for up to a three year project.
b. Fill in the baseline values for each indicator including the date it was collected and the unit of measurement. If the baseline values do not come from a consolidated baseline survey, note in the status column where the values are archived (the document, file, government database, etc). The baseline values are automatically populated in the Year 2 and Year 3 ITTs in the blank workbook.
4. Set indicator targets:
a. Indicator targets should be set for each indicator based upon the details outlined in the project proposal taking into consideration timelines, number of staff, and budget. Start with Life of Project (LOP) targets, then annual targets, then quarterly targets. Targets should be based on the project’s work plan/detailed implementation plan.
i. All targets and actuals should be cumulative. This means that targets and actuals recorded for each quarter reflect what has been targeted or achieved to date. If a given indicator cannot be recorded in a cumulative manner for some reason, include a note in the status column.
ii. Values for indicators should be numeric with narrative detail reserved for the Narrative Report.
iii. LOP targets will be included in each ITT on an annual basis. The LOP targets should remain the same throughout, but in each new annual ITT any cumulative data should be transferred.
iv. Impact indicators (Outcome and Goal) are often measured at the start of project (baseline) and end of project (endline) and therefore will only require LOP targets.
b. The values in the "Target" and "Actual" columns should be entered as whole numbers, not percentages. This will help to ensure that the numerator and denominator are clearly expressed, which reduces calculation errors.
c. Formulas can be used in Excel so that percentages and other calculations are done automatically, reducing the amount of data that must be entered manually. However, formulas can be tricky and should be double-checked to ensure that the data has been calculated correctly.
5. Using the Indicator Tracking Table:
a. Actual data reported should be confirmed data that has been collected during the reporting period, not estimates or guesses. If you are confused about what an indicator means or how to enter the data, refer to your project’s M&E Matrix.
b. The ITT should be filled out on a quarterly basis, before starting work on the Project Progress Report.
c. Some indicators will require the roll-up of data from multiple communities, districts, regions, etc. The data from each individual source should be kept in a table on another tab within this file, with the sum linked to the Actual column for that indicator. This will help assist in data verification.
d. Make sure to update actual beneficiary numbers in the ITT in each project reporting period.
6. Complete the Activity Tracking Table: The ATT is a complimentary tool to the ITT. It allows activities to be tracked in a summary manner in a separate tab from the indicators so that the progress towards the project indicators in the ITT can be easily read. See tab k. for further instructions on using the ATT.
a. List the high level projects activities in the first column as outlined in the project proposal. Make sure that the activities listed under each Output are associated specifically with that Output.
b. Complete the "targets" for each activity for each reporting period, year, and LOP based upon the project's detailed implementation plan.
c. The ATT should be filled out on a quarterly basis with activities accomplished during the reporting period.
d. For each reporting period, update the status of the activity in column W. It should be updated with "Not yet started," In progress," or "Completed." If it is completed, list the date completed.

## b. M&E Matrix Description
TOOL SUMMARY: M&E MATRIX INSTRUCTIONS
Purpose | The purpose of this tool is to guide staff to complete each column of the M&E Matrix.
· The M&E Matrix is a critical tool for planning and managing data collection, analysis, and use. It expands on the Logframe to identify key information requirements for each indicator and summarizes the key M&E tasks for the project.
o It helps staff determine if a proposed indicator can effectively measure the result to which it is linked.
o It helps staff determine if the proposed indicators can feasibly be collected given time and resource constraints.
Information Sources | Information the project team should have before starting the M&E Matrix:
· Logframe
· Project Proposal (Initial M&E Plan)
Guidance for M&E Matrix:
· CRS SMILER Guide
Who | This tool is a reference that can be used as a reference for any staff working to complete the M&E Matrix
When | Given that the M&E Matrix helps define the scope (cost, time) of the project’s monitoring system, it is recommended that the Indicator Definition, Frequency/Schedule, and Responsible Person columns be completed before finalizing the project proposal.
The remaining columns of the M&E Matrix should be filled out as the information becomes available, but must be finalized within the following timeframes:
· Projects 1 year or less: complete a detailed M&E plan within 60 days of the project approval
· Projects with a duration of 1-3 years: complete a detailed M&E plan within 90 days of the project approval
· Projects with a duration of 3-5 years: complete a detailed M&E plan within 120 days of project approval
Requirements | REQUIREMENTS:
· This M&E Matrix should be used for all LWR projects.
· The M&E Matrix is a living document and should be updated based upon relevant project adjustments
o If the M&E Matrix is changed report the changes, the reason, and how it affects other aspects of the M&E and project implementation plan
o If changes are made to the plan, ensure that HQ, the country office, and the partner have the updated version
RECOMMENDATIONS:
· Ideally, the M&E Matrix will be finalized during a joint project planning meeting (project kick-off meeting) with participation from both key partner and LWR staff.
SMART Criteria:
· SMART criteria are: Specific, Measurable, Attainable, Relevant, and Timebound.
· It is recommended that objective statements in the Logframe are NOT written using SMART criteria.
o Nevertheless, SMART objective statements can sometimes be used effectively within project proposals to show all the details of the expected result in one statement.
· SMART criteria should be applied to indicators, not objective statements. (reference p. 37 of IFRC Project Planning Guidance Manual for further information on SMART criteria).
· Follow the instructions and examples for writing indicators found in the Logframe Cheat Sheet.
· As presented in the Logframe, each indicator may not meet all the SMART criteria, but once the M&E Matrix is fully developed the indicators should be SMART.
Tips | · The M&E Matrix should be completed by those who will be using it. This allows the project team to crosscheck the Logframe and indicators before project implementation (ensuring they are sensitive to field realities and team capacities). Team involvement is essential because the M&E Matrix requires their detailed knowledge of the project context, and their involvement reinforces their understanding of what data they are to collect and how they will collect them.
· Keep the M&E Matrix plan appropriate for the scale and timeframe of the project. Remember, it should be ‘good enough’.
· Double check that your indicators can be measured in a realistic manner. Balance qualitative and quantitative data to measure indicators.
· Make sure to be clear who within the project team is responsible for “owning the M&E Matrix.” This includes ensuring it is thoroughly completed, that all relevant project stakeholders understand it and have copies of it, that any changes made are fully incorporated and shared, and to regularly monitor and manage that all outlined tasks are being completed. The same person should also be responsible for managing the Indicator Tracking Table and the Activity Tracking Table.
· The M&E Matrix is nearly identical to USAID’s Performance Monitoring Plan. The instructions for the M&E Matrix can be applied to complete USAID’s PMP.
Gender Considerations | A project that meets the LGI standards for gender integration at this stage will undertake all of the following:
· Sex-disaggregate data of all indicators for which people are the unit of measure.
· Include qualitative and quantitative indicators .

## c. M&E Matrix Cheat Sheet
M&E Matrix Cheat Sheet [1]
PERFORMANCE INDICATORS |  | DATA GATHERING |  |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Method | Means of Verification (Data Source/Tools) | Frequency & Schedule | Responsible Person | Data Analysis | Information Use/Audience | Reporting
- Indicators are taken from the logframe. When transferring them, check to ensure they are SMART (specific, measureable, achievable, relevant, and time-bound). - Often, the indicator may need to be revised according to field realities. If this is the case, be sure any revisions are approved by LWR and/or the donor. - If indicators are updated here, ensure the logframe is also updated. | - Each indicator needs a detailed definition of its key terms, including an explanation of specific aspects that will be measured (such as who, what, and where the indicator applies). - Define subjective words as necessary, such as “appropriate,” “successful,” “sustainable,” “sufficient,” “capacity,” etc. - The definition should explain precisely how the indicator will be calculated, such as the numerator and denominator of a percent measure. It should specify the unit of measure. - This column should also note if the indicator is to be disaggregated by sex, age, ethnicity, or some other variable. | -This column states the method by which data will be collected. These can include approaches such as use of secondary data, regular monitoring, baseline or endline surveys, PRA, focus group discussions, etc. -The method should match the Means of Verification. For example, if the method is ‘regular monitoring,’ the means of verification should be some type of report regularly produced by project staff. | - This column identifies sources of information. - If multiple sources are listed, it must be clear how the information in the various sources will come together to make one data point for the indicator. A master data sheet may be required for an indicator. - This column should also indicate whether data collection tools (questionnaires, checklists) are pre-existing or will need to be developed. - The logframe column on “Means of Verification” may list a source or method, i.e., “household survey.” The M&E plan requires much more detail, since the M&E work will be based on the specific methods noted. | - This column states how often the data for each indicator will be collected (monthly, quarterly, annually). - The frequency listed must match the targets set in the Indicator Tracking Table. - It is useful to list the data collection timing or schedule, such as start-up and end dates for collection or deadlines for tool development. - When planning for data collection timing, it is important to consider factors such as seasonal variations, school schedules, holidays, and religious observances (i.e. Ramadan). | - This column lists the people responsible and accountable for the data collection and analysis, i.e., community volunteers, field staff, project managers, local partner/s, and external consultants. - In addition to specific people’s names, use the position title to ensure clarity in case of personnel changes. - This column is useful to budget for M&E staff and planning for their capacity building. | - This column describes the process for compiling and analyzing the data. This process gauges if the indicator has been met. - For example, survey data usually requires statistical analysis, while qualitative data may be reviewed by research staff or community members. - Include any questions that the project team may want to ask to better understand the data once it is compiled. | - This column identifies the intended audience and use of the information. - For example, the findings could be used for monitoring project implementation, evaluating the interventions, planning future project work, or reporting to policy makers or donors. - Defining how you will use the information helps eliminate unnecessary indicators or analysis. The data should be linked clearly to decision making and/or accountability. - Reduce the quantity and frequency of data collection if the tabulation and analysis cannot be done in time for decision-making or communications and reporting. | - It is important to identify in which reports each indicator data will appear. Communication and reporting mapping will assist in identifying where each indicator is reported. - This column should also state ways that the findings will be formatted (tables, graphs, maps, histograms, narrative reports). This will help to ensure that only the most relevant data and information is reported to each stakeholder, and will increase the likelihood of feedback on reported information.
[1] M&E Plan Matrix template was derived from IFRC’s M&E Plan Template (April 6, 2011): http://ifrc.org/en/who-we-are/performance-and-accountability/monitoring-and-evaluation/, and CRS’ ProPak. The content for the instructions were borrowed primarily from IFRC’s M&E Plan Template (April 6, 2011) with additional content borrowed from CRS’ M&E in Emergencies, DESIGN: How to develop an M&E plan in an emergency project M&E Plan Template, Appendix 3, p. 54.

## d. M&E Matrix Example
Project Name: |  | Project Location: |  |  |  | Project Year:
Identifier |  | Partner: |  |  |  | Project Start Date:
Project Sector(s): | [5 empty] | Project End Date:
PERFORMANCE INDICATORS |  | DATA GATHERING |  |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Method | Means of Verification | Frequency and Schedule | Reponsible person/ team | Data Analysis | Information Use/Audience | Reporting
GOAL: Communities living along Nepal- India boarder in the Gandak, Narayani and Koshi rivers basin have achieved a better quality of life through increased resilience to the impact of flooding
OUTCOME 1: Communities living along the Nepal-India border in the Gandak, Narayani and Koshi river basin have increased their adaptive capacity
Indicator 1.a: % of households have accessed financial services/capital for their livelihood activities | Unit: Household, Calculation: (number of hh accessing financial services/ total number of targeted hh)*100 have accessed financial services/capital: access and use of financial services/capital for diversified livelihood income from any source (external, self-help groups, cooperatives, etc.) | On-going Monitoring and household visit; consultant baseline | Project Coordinator database Social Mobilizer report/Activity Record Cooperative or Self-Help Group Records | Quaterly Monthly Ongoing | Project Coordinator Agricultural Technical Specialist (Social Mobilizer) Cooperative or Self-Help Group secretary | Is the % of households accessing financial services increasing over time? | LWR country offices Partners Cooperative or Self-Help group | Project Coordinator Quarterly
OUTPUT 1.1: Target communities have improved access to financial services
Indicator 1.1.a: # of saving and credit groups/cooperatives formed and strengthened | Unit: Number of Saving and Credits groups Calculation: Count number of formal/informal gropus involved in saving and Credits, Savings and Credit Group/Cooperative: Regulating fund mobilization at the community level Formed: created Strengthened: trained on purpose, norms | Ongoing monitoring; Cooperative/self-help group meetings Partner responsible for Baseline data | ITT Project Coordinator database Social Mobilizer report | Quarterly Quarterly Monthly | Program Manager Project Coordinator Social Mobilizer | Is the number of groups increasing over time? Are the groups getting stronger and/or improving their ability to provide service? | Partners | Quarterly

## e. M&E Matrix (Blank)
“Project Name” M&E Matrix
Project Name: |  | Project Location: |  |  | Project Year:
Identifier: |  | Partner: |  |  |  | Project Start Date:
Project Sector(s): | [5 empty] | Project End Date:
PERFORMANCE INDICATORS |  | DATA GATHERING |  |  |  | ANALYSIS, USE, REPORTING
Indicator | Indicator Definition | Method | Mean of Verification | Frequency and Schedule | Reponsible person/ team | Data Analysis | Information Use/Audience | Reporting Deadline
GOAL:
OUTCOME 1:
Indicator 1.a:
Indicator 1.b:
OUTPUT 1.1:
Indicator 1.1.a:
Indicator 1.1.b:
OUTPUT 1.2:
Indicator 1.2.a:
Indicator 1.2.b:
OUTCOME 2:
Indicator 2.a:
Indicator 2.b:
OUTPUT 2.1:
Indicator 2.1.a:
Indicator 2.1.b:
OUTPUT 2.2:
Indicator 2.2.a:
Indicator 2.2.b:
OUTCOME 3:
Indicator 3.a:
Indicator 3.b:
OUTPUT 3.1:
Indicator 3.1.a:
Indicator 3.1.b:
OUTPUT 3.2:
Indicator 3.2.a:
Indicator 3.2.b:
OUTCOME 4:
Indicator 4.a:
Indicator 4.b:
OUTPUT 4.1:
Indicator 4.1.a:
Indicator 4.1.b:
OUTPUT 4.2:
Indicator 4.2.a:
Indicator 4.2.b:
Note on A7: The content in Column A is linked to the ITT. This makes the content entered here automatically copied to the ITT.

## f. Baseline Table Description
TOOL SUMMARY: BASELINE TABLE
Purpose | The purpose of this tool is to ensure that all relevant, and only relevant, baseline data information is collected and documented. The baseline information is later used to determine targets. NOTE: The Baseline is NOT a Needs Assessment. The Baseline collects starting data for indicators and should not seek to collect information that will require the project theory of change to be adjusted.
Information Sources | Information the project team should have before starting work on the Baseline:
· Complete M&E Matrix
· Project Proposal (Initial M&E Plan)
Who | One person should be chosen to lead the baseline process. This person is responsible to ensure the table is completed, but is not necessarily responsible for collecting all the data. If a consultant is hired to collect primary data, he/she should be responsible for completing the table for the assigned indicators.
When | According to the IPD policy regarding the submission of Detailed M&E Plans and indicator baseline values of projects starting as of April 1, 2014, the final submission of the Detailed M&E Plan (M&E Matrix, Baseline Table, and the Indicator Tracking Table) must not exceed the following deadlines:
· Projects of less than one year of duration: 60 days from project start date
· Projects between one and three years of duration: 90 days from project start date
· Projects between three and five years of duration: 120 days from project start date
Requirements | REQUIREMENTS:
· Filling out this table is required for all UNRESTRICTED projects.
· For RESTRICTED projects, donor requirements should be followed. If there are no donor requirements, default to these guidelines.
· If a consultant is hired, he/she should provide a database with all the cleaned data from surveys for project records to ensure transparency and validity.
· The information contained in the Baseline Table should only be modified if changes are made to indicators or their definitions that respond to specific and documented technical feedback that complies with donor and LWR standards.
o If changes are made, document and report the reason why the changes were made and how it will impact any other aspects of the project's M&E system and/or project implementation. It is recommended not to eliminate the rows of the indicators that have been changed. Rather, it is suggested to create another row to record the new version of the indicator even if only minor changes have been made to the definition or any other aspect of it. The Comments column can also be used to explain all that is considered worth explaining.
o If changes are made to the Baseline Table make sure LWR´s headquarters, the country office and the partner have and use the up-to-date version.
o LWR staff need to ensure that the most up-to-date document is in Phoenix.
Tips | · Those who will use the Baseline Table should fill it out. This allows the project team to verify their understanding of the definition and method used to collect the baseline data and use this same understanding for ongoing data collection or data collection at the end of the project (endline).
· Make sure to define who should take "ownership" of the Baseline Table. This involves ensuring that the table is finalized, that all the interested parties understand the information contained in it and have the final versions, and that any future changes are fully incorporate into the project plan and shared with all stakeholders.
o The same person should be in charge of the Indicator Tracking Table and the Activity Tracking Table.
· If the baseline is being conducted internally and there are questions about sample size calculations, contact your relevant M&E representative.
· Baseline studies establish the starting point for each indicator which is necessary for determining if indicator targets defined in the project design need adjustment.
Gender Considerations | A project that meets the LGI standards for gender integration at this stage will undertake all of the following:
· Sex-disaggregate data of all indicators for which people are the unit of measure.
· Include qualitative and quantitative indicators .

## g. Baseline Table Cheat Sheet
Indicator table for the Baseline of "Name of the Project"
Name of the project: |  |  | Location of the project: |  |  | Project duration (in years):
Identifier: |  |  | Partner: |  |  | Project start date:
Sector(s) of the project: | [5 empty] | Project end date:
INDICATORS |  |  | TARGETS AND BASELINE VALUES |  |  | DOCUMENTATION
Indicator | Indicator definition | Unit of measurement | Life of project target | Baseline value | Date of the baseline value | Source of the baseline value | Comments
Indicators are taken directly from the M&E Matrix. Include all indicators as even indicators with a zero starting value should have documented justification for this value. | Indicator definitions come directly from the M&E Matrix. They are repeated here only for ease of reading and understanding their definitions in relation to the baseline values. Refer to the M&E Matrix Cheat Sheet for more information on indicator definitions. | A unit of measure is a standard quantity that serves to establish the magnitude of the value of an indicator. It answers the question: What are we counting? Units of measure often used in LWR projects are: Simple (one element): people kilos or pounds tons plot hectares Best practices Complex (more than one element): productivity: Kilos or tons per hectare density: trees per plot or hectare poverty: Income per year Income per year per hectare | This is the value of the indicator that the project team hopes to achieve by the end of the project. It is expressed in the unit of measurement defined in column C. Example: 300 people trained in soil management practices, 100 coffee plantations managed with best pruning practices, cacao productivity of 2 tones per hectare, net income of $150 per family from legume sales For quantitative indicators based on mathematical formulas (Ex.: percentage, rate, etc) it is suggested to redocument the components of the formula (the values that make up the numerator and the denominator). | This is the value of the indicator at the beginning of the project. This value is expressed in the same unit of measure as the target. OUTPUT indicators: OUTPUT baseline values are often zero (0) as these type of indicators are used to measure the results of implementing project activities. However, depending on how the logframe was built, OUTCOME indicators such as production and productivity could be assigned to the OUTPUT LEVEL (Ex. Three tons of potatoes per hectare per year). Examples of common OUTPUT indicators: N° of people trained, N° of infrastructures built, N° of pieces of equipment delivered, N° of plans developed and approved, N° of contracts signed with cacao buyers. OUTCOME indicators: are located above the OUTPUTS in the chain of the project's intended results and refer to conditions already present in the target population that can be measured to show change. They normally measure a change in behavior, attitudes and/or practices. Examples of common OUTCOME indicators: N° of producers who consistently apply best practices, N° of students who wash their hands according to the five key steps, annual net family income from coffee sales. | The date (month and year) when the initial value (Ex. 250 pounds per hectare per year) was gathered in the field from a primary source (Ex. A producer survey, a coop´s production registries). If the value is obtained from a secondary source (a needs assessment, an agrarian census, baselines or studies by other organizations, etc) it may not be possible to know the date when value for the indicator was actually gathered. In that case, put the publication date of the document. | Refers to the document (in physical or electronic format) in which the indicator value is stated. These documents can be either primary or secondary sources. Primary sources are data that were collected directly by LWR or its partners. These include household surveys, registries, databases, various types of reports, etc. It is important to state the type of document that contains the value for the indicator (Ex. A coop´s registry of cacao sales). Secondary sources are those that LWR or its partners did not collect directly. They include agrarian or other types of census, studies by international organizations such as the UN, LWR peer organizations or LWR partners not participating in the project. It is necessary to be explicit with regards to the title of the document and the author(s), be it an institution or a person, and the publication date. If the value of the indicator was taken from a Website (Ex. From the Ministry of Agriculture or from the National Statisics Department) it is important to document the URL and it is also recommened to save a copy of the screen (use the print screen function) which states the date in which that data was collected. | This is a space to put information about the indicator that is deemed by the project team to be of value to better understand the project results. Complementary information can refer to any of the aspects addressed in the preceeding columns. Some examples are: (i) for an indicator of production or productivity, if the original unit of measure was a locally used one (Ex. Manzanas in Nicaragua) and was transformed to hectares due to a donor´s request, it can be explained in this section putting the equivalence between manzanas and hectares (1 mz=0.7 Has), (ii) if the indicator value corresponds to some of the geographic areas participating in the project and not to others it can be explained here, (iii) if the indicator value was obtained using a sample of a certain type (Ex. Probabilistic, by quotas, voluntary, etc.) or a census.

## h. Baseline Table (Blank)
Indicator table for the Baseline of "Name of the Project"
Name of the project: |  |  | Location of the project: |  |  | Project duration (in years):
Identifier: |  |  | Partner: |  |  | Project start date:
Sector(s) of the project: | [5 empty] | Project end date:
INDICATORS |  |  | TARGETS AND BASELINE VALUES |  |  | DOCUMENTATION
Indicator | Indicator definition | Unit of measurement | Life of project target | Baseline value | Date of the baseline value | Source of the baseline value | Comments
GOAL:
OUTCOME 1:
Indicator 1.a:
Indicator 1.b:
OUTPUT 1.1:
Indicator 1.1.a:
Indicator 1.1.b:
OUTPUT 1.2:
Indicator 1.2.a:
Indicator 1.2.b:
OUTCOME 2:
Indicator 2.a:
Indicator 2.b:
OUTPUT 2.1:
Indicator 2.1.a:
Indicator 2.1.b:
OUTPUT 2.2:
Indicator 2.2.a:
Indicator 2.2.b:
OUTCOME 3:
Indicator 3.a:
Indicator 3.b:
OUTPUT 3.1:
Indicator 3.1.a:
Indicator 3.1.b:
OUTPUT 3.2:
Indicator 3.2.a:
Indicator 3.2.b:
OUTCOME 4:
Indicator 4.a:
Indicator 4.b:
OUTPUT 4.1:
Indicator 4.1.a:
Indicator 4.1.b:
OUTPUT 4.2:
Indicator 4.2.a:
Indicator 4.2.b:

## i. ITT Description
TOOL SUMMARY: INDICATOR TRACKING TABLE INSTRUCTIONS
Purpose | The Indicator Tracking Table (ITT) is a tool that is used as a tracking mechanism for all project indicators.
Information Sources | Information the project design team should have before starting the ITT:
· Needs Assessment
· Logframe
· Project Proposal
· Baseline Data
· M&E Matrix
Who | The ITT should be completed by the partner, reviewed by the LWR PM, and included in each Project Progress Report
When | The ITT is a sub-tool of the Detailed M&E Plan and should therefore be completed according to the timeframe set out for the completion of the Detailed M&E Plan. It is normally developed after the M&E Matrix has been completed and after the baseline data has been collected.
Requirements | REQUIREMENTS:
· Every project is required to have an ITT.
· The ITT requires setting targets for indicators on quarterly, annual, and life of project timeframes.
· The ITT should be updated with actual data for every reporting period. The ITT should be updated before beginning the narrative Project Progress Report.
o The ITT is a very useful management tool and is most effective when used on a quarterly basis. Use on a quarterly basis provides project managers with more regular data and can help in making timely adjustments and improvements to the project.
· If the required reporting period is semiannually, it is suggested that the ITT be completed on a quarterly basis, but that the analysis included in the Project Progress Report focus on progress for the entire six month period.
RECOMMENDATIONS:
· Targets can be revised, but there should be clear and convincing reasoning behind the revision. Indicator target revisions are not common and should be done only when there has been a major change to the scope or context of the project.
o For restricted projects, consult with the LWR Grants Manager before revising indicator targets. Target revisions should also be communicated clearly to the donor.
o For unrestricted projects, coordinate with the Program Associate before revising indicator targets.
o If approval is given to revise indicator targets:
§ Highlight revised targets in progress reports and provide clear and specific reasoning for the revisions.
§ Ensure that new targets are updated in the ITT and that all subsequent quarterly targets and annual and life of project targets reflect the revision.
· The “Status” column in the ITT can indicate the date the indicator data is expected to start and end, if it will only be collected at baseline and endline, if it is completed, or if it is ongoing. The “Status” column is NOT to be used to provide any narrative explanation about the indicator. This should be done in the Project Progress Report.
Tips | · Not meeting a target should be viewed as a learning experience, not as a failure.
o Discussions about why actual data is over or under a target is important.
o Set ambitious targets, but also make them realistic by linking them as closely as possible to the project’s detailed implementation plan.
· Use the ITT as a key analysis and reporting tool.
o Analyze why or why not targets were met to help you understand what adjustments to the project’s implementation should be made.
· Key findings from the analysis becomes central information for project reports, and can be shared with all relevant stakeholders.

## j. ITT "Project Name" Year 1
LUTHERAN WORLD RELIEF INDICATOR TRACKING TABLE | [17 empty] | Project Beneficiaries
Project Name: | [18 empty] | Female | Male | Total
Report Period: |  |  |  | Partner: | [6 empty] | Project Year | [6 empty] | Direct |  |  | 0
Identifier: |  |  |  | Project Location: | [6 empty] | Project Start Date: | [6 empty] | Indirect |  |  | 0
Project Sector(s): | [10 empty] | Project End Date: | [6 empty] | Total | 0 | 0 | 0
RESULTS |  | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target | Project Component | Status
|  | Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
GOAL:
OUTCOME 1:
Indicator 1.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 1.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 1.1:
Indicator 1.1.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 1.1.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 1.2:
Indicator 1.2.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 1.2.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS |  | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
|  | Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTCOME 2:
Indicator 2.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 2.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 2.1:
Indicator 2.1.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 2.1.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 2.2:
Indicator 2.2.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 2.2.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS |  | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
|  | Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTCOME 3:
Indicator 3.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 3.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 3.1:
Indicator 3.1.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 3.1.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 3.2:
Indicator 3.2.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 3.2.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS |  | Project Baseline |  |  | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
|  | Date | Value | Unit | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTCOME 4:
Indicator 4.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 4.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 4.1:
Indicator 4.1.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 4.1.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 4.2:
Indicator 4.2.a: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Indicator 4.2.b: | [6 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Men | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
| Women | [5 empty] | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
Note on Z7: The “Status” column in the ITT can indicate the date the indicator data is expected to start and end, if it will only be collected at baseline and endline, if it is completed, or if it is ongoing. The “Status” column is NOT to be used to provide any narrative explanation about the indicator. This should be done in the Project Progress Report.

## k. ATT Description
TOOL SUMMARY: ACTIVITY TRACKING TABLE INSTRUCTIONS
Purpose | The Activity Tracking Table is a complimentary tool to the Indicator Tracking Table. It allows activities to be tracked in a summary manner and in a separate tab. This helps show project progress towards achieving the project’s outputs without complicating the ITT.
The ATT is a tool that is used in assisting the project team, the LWR PM, and LWR HQ track progress on the completion of planned activities. The ATT elaborates on the general Project Work Plan contained in the Project Design Workbook by listing all project activities and the estimated targets for each reporting period.
Information Sources | Information the project team should have before starting the ATT:
· Logframe
· Project Proposal
· M&E Matrix
· Indicator Tracking Table
Who | The ATT should be completed and updated by the partner, reviewed by the LWR PM, and included in each Project Progress Report.
When | The ATT is a sub-tool of the Detailed M&E Plan and should therefore be completed according to the timeframe set out for the completion of the Detailed M&E Plan.
Requirements | REQUIREMENTS:
· The ATT is not required.
RECOMMENDATIONS:
· The ATT is linked to the ITT and is used to track project progress. It therefore has similar requirements and recommendations as the ITT.
· The completion of activities tells us little about changes in development conditions or in the lives of people. It is the results of these activities that is significant. Nevertheless, tracking the completion of planned activities is a very important management tool. LWR therefore encourages the use of the ATT instead of including the tracking of activities in the ITT or in a logframe template.
· Every project should have a system to track Activities, but the project is not required to use LWR’s template.
· The ATT should be updated with actual data for every reporting period. The ATT should be updated before beginning the narrative Project Progress Report.
o The ATT is a key management tool and is most effective when used on a quarterly basis. Use on a quarterly basis provides project managers with more regular data and can help in making timely adjustments and improvements to the project.
o If the required reporting period is semiannually, it is suggested that the ATT be completed on a quarterly basis, but that the analysis included in the Project Progress Report focus on progress for the entire six month period.
· Setting targets for the number of activities to be completed in a reporting period is a way to ensure that all activities are completed by the end of the project. LWR understand that many factors affect the completion of activities according to plan. Nevertheless, the project should strive to complete activities as planned, which is most easily measured by tracking the completion of activities according to targets.
o Section 3.1.a. of the Project Progress Report is dedicated to an analysis of the progress towards meeting activity targets. This will allow the project team to explain in more detail the simplified quantitative activity tracking of the ATT.
Tips | · Not meeting a target should be viewed as a learning experience, not as a failure.
o Discussing why actual data is over or under a target is important.
o Set ambitious targets, but also make them realistic by linking them as closely as possible to the project’s detailed implementation plan.
· Use the ATT as a key analysis and reporting tool
o Analyze why activity targets were or were not met, analyze them in the context of how they relate to meeting impact indicator targets, and use the results to help you determine any adjustments to the project’s implementation plan that should be made.
o Key findings from the analysis becomes central information for project reports, and can be shared with all relevant stakeholders.
· Reporting detailed information about sub-tasks to complete activities can be time-consuming and confusing for report reviewers at the regional and Headquarters level. Keep it simple, clear, and concise.

## l. ATT "Project Name" Year 1
LUTHERAN WORLD RELIEF ACTIVITY TRACKING TABLE
Project Name:
Report Period: | Partner: | [5 empty] | Project Year
Identifier: | Project Location: | [5 empty] | Project Start Date:
Project Sector(s): | [6 empty] | Project End Date:
| Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target | Project Component | Status
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 1.1:
ACTIVITY 1.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.1. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 1.2:
ACTIVITY 1.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.2. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 1.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 2.1:
ACTIVITY 2.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.1. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 2.2:
ACTIVITY 2.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.2. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 2.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 3.1:
ACTIVITY 3.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.1. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 3.2:
ACTIVITY 3.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.2. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 3.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
RESULTS | Q1 Reporting Period Date X - Date Y |  |  | Q2 Reporting Period Date X - Date Y |  |  | Q3 Reporting Period Date X - Date Y |  |  | Q4 Reporting Period Date X - Date Y |  |  | Annual Target | Year to Date Actual | % of Annual Target | Life of Project Target | Life of Project Actual | % of LoP Target
| Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
OUTPUT 4.1:
ACTIVITY 4.1. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.1. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.1. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
OUTPUT 4.2:
ACTIVITY 4.2. A: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.2. B: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA
ACTIVITY 4.2. C: |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | NA